## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-II water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 1301/BD | 26/04/2023 | 01/12/2024 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 766.02 | 0 | 0 | 29
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-I B water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2023-2024 | 1694/BD | 08/06/2023 | 06/09/2023 | SUPRITI ENTERPRISE. | 581.97 | 0 | 0 | 20
3 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-I A water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2023-2024 | 1726/BD | 08/06/2023 | 06/09/2023 | SUJIT KUMAR SAHA | 224.48 | 34.43 | 15.34 | 10
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Rep.) and IV (New) under Gokna W/S Scheme and Pump House No- II (Rep) under Arsula W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001912/2023-2024 | 6735/EMD | 29/11/2023 | 01/04/2025 | M.S. ENTERPRISE | 39.12 | 0 | 0 | 30
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Hiring Diesel Luxury Car on daily basis for the supervision of work and office uses under Basirhat Sub-Division P.H.E. Dte. (Period: 01.07.2024 to 31.12.2024), Sl.No. - 02 | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 1018/BHTSD | 28/06/2024 | 29/12/2024 | DEB KUMAR DAS. | 0.87 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Baduria Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte | Assistant Engineer |  | ORD/001008/2024-2025 | 3553/BD | 16/12/2024 | 15/01/2025 | PRITAM MUKHOPADHYAY. | 60.15 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1248/BD | 25/04/2023 |  | Resource Division | 520.48 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 4424/BD | 10/11/2023 |  | Resource Division | 47.88 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03461/2023-2024 | BP-2023-24-830 | 15/03/2024 |  | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 76.53 | 0 | 0 | 0
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | SM/13405 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03461/2023-2024 | BP-2023-24-830 | 15/03/2024 |  | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 76.53 | 0 | 0 | 0
Total | [13 empty] | 23733.79 | 34.43 | 0.15