## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002718/2021-2022 | 281/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.09 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002994/2021-2022 | 281/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.09 | 0 | 0 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | New | Material Requisition To Resource Division |  |  | RTOR000209/2022-2023 | 885/BD | 22/03/2023 | 22/03/2023 | Resource Division | 14.83 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Kachurhula w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 1524/BD | 19/05/2023 | 01/01/2026 | ROY CHOWDHURY CONSTRUCTION. | 147.05 | 0 | 0 | 96
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme | SM/13445 | New | Acceptance cum work order for Protection works in different places for protection of different dia DI-UPVC rising/distribution pipe line by UC bullah/bamboo pile for Kachurhula Zone-II w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000060/2025-2026 | 1610/BD | 19/05/2025 | 18/06/2025 | SARKAR ENTERPRISE & CO. | 15.55 | 0 | 0 | 0
Total | [13 empty] | 21523.38 | 0 | 0