## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Matiagachha Water Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002951/2021-2022 | 833/BSD | 16/12/2021 | 15/01/2022 | M.ENTERPRISE. | 1.85 | 1.75 | 94.66 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Matigacha (Block:-Barasat-II) W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001140/2023-2024 | 4742/EMD | 07/08/2023 | 06/09/2023 | M.D. ENTERPRISE | 21.37 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Repairing & Renovation of 1 No. Pump House (P.H. No-II) and allied works at Matiagachha Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002956/2021-2022 | 837/BSD | 20/12/2021 | 19/01/2022 | K.D ENTERPRISE. | 1.25 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1285/BD | 25/04/2023 | 25/04/2023 | Resource Division | 46.16 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1673/BD | 06/06/2023 | 06/06/2023 | Resource Division | 46.16 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1676/BD | 06/06/2023 | 06/06/2023 | Resource Division | 11.83 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 4375/BD | 10/11/2023 | 10/11/2023 | Resource Division | 12.98 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at Matiagacha Water Supply Scheme under Barasat-II Block, under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000568/2024-2025 | 3080/BD | 29/10/2024 | 28/11/2024 | SANTU GHOSH. | 25.1 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Preparation of DPR in connection of augumentation of Matiagachha Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-20 | Assistant Engineer | Junior Engineer | ORD/000313/2022-2023 | 567/BSD | 29/06/2022 | 29/07/2022 | RADIANT | 3.27 | 2.76 | 84.59 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Matiagacha Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2023-2024 | 2942/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 11.91 | 73.92 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001783/2023-2024 | 627/BD | 28/02/2024 | 13/04/2024 | R.K.MANDAL & CO. | 23.11 | 23.03 | 99.66 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Matiagachha water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2023-2024 | 1715/BD | 08/06/2023 | 08/06/2024 | MITRA CONSTRUCTION. | 378.68 | 141.81 | 37.45 | 39
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Matiagachha Water Supply Scheme within Barasat-II Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001157/2024-2025 | 98/BD | 09/01/2025 | 18/02/2025 | AMIT KUMAR BOSE. | 9.19 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Construction of Pump House with latrine at Matiagachha water Supply Scheme under Barasat-II Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. |  | Junior Engineer | ORD/001384/2024-2025 | 1022/BSD | 03/01/2025 | 12/02/2025 | BUSTER CONSTRUCTION | 4.87 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Acceptance cum work order for Additional Laying of UPVC pipe line and allied work in connection with Augmentation Matiagachha Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001050/2024-2025 | 57/BD | 07/01/2025 | 06/02/2025 | MITRA CONSTRUCTION | 37.61 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | SM/13446 | Augmentation | Acceptance cum work order for Repair & Renovation work at Different site in connection with Augmentation of Matiagacha Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002047/2024-2025 | 930/BD | 24/03/2025 | 08/05/2025 | AREOCON. | 9.03 | 0 | 0 | 100
Total | [13 empty] | 648.6 | 181.27 | 27.95