## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Preparation of DPR in connection of augumentation of Nebadhui Duttapukur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000680/2022-2023 | 457/BSD | 20/05/2022 | 19/06/2022 | RADIANT | 3.7 | 3.34 | 90.41 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Formal work order for Construction of 550 cum capacity 20Mtr. Height R.C.C. Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001201/2023-2024 | 4122/BD | 17/10/2023 | 01/07/2025 | M/S B.K.ENTERPRISE. | 598.56 | 105.24 | 17.58 | 35
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 4021/BD | 12/10/2023 | 12/10/2023 | Resource Division | 24.5 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1281/BD | 25/04/2023 | 25/04/2023 | Resource Division | 86.51 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Nebhadui Duttapukur Z-II Water Supply Scheme under JJM programme in Barasat-I block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001018/2024-2025 | 3737/BD | 27/12/2024 | 27/03/2025 | M/S B.K.ENTERPRISE. | 100.4 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (3rd Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000470/2024-2025 | 585/BSD | 10/09/2024 | 30/09/2024 | MANGES INDUSTRIAL CORPORATION. | 2.82 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Repair and Renovation Work of Pump House at 3rd Tubewell site and allied works at Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000466/2024-2025 | 584/BSD | 10/09/2024 | 30/09/2024 | MANGES INDUSTRIAL CORPORATION. | 2.51 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Repair and Renovation Work of Pump House at 2nd Tubewell site and allied works at Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000464/2024-2025 | 582/BSD | 10/09/2024 | 01/12/2024 | M/S S.HAQUE & CO. | 2.55 | 1.25 | 48.83 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (2nd Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000465/2024-2025 | 583/BSD | 10/09/2024 | 30/09/2024 | NEW MA TARA ENTERPRISE. | 2.47 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (1st Tubewell - Pump House). |  | Junior Engineer | ORD/001103/2024-2025 | 1005/BSD | 02/01/2025 | 22/01/2025 | ROMI TREDERS. | 3.89 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | SM/13469 | Augmentation | Restoration charges for laying of pipeline along Duttapukur Railway Gate no-I to Duttapukur Bus stand Road bus Stand road Nebhadhui Duttapukur-II Water Supply Scheme Under Barasat sub division, PHE Dte.under JJM Programme along santoshpur- Duttapukur road From 4.50 km TO 5.974 km Under Barasat Highway Division no-II In the District of North 24 Parganas . |  |  | BILL/01621/2024-2025 | BP-2024-25-479 | 28/01/2025 | 28/01/2025 | EXECUTIVE ENGINEER, PWD HIGHWAY DIVISION NO II | 28.13 | 0 | 0 | 0
Total | [13 empty] | 856.03 | 109.83 | 12.83