## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1674/BD | 06/06/2023 | 06/06/2023 | Resource Division | 14.7 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 4373/BD | 10/11/2023 | 10/11/2023 | Resource Division | 16.37 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1280/BD | 25/04/2023 | 25/04/2023 | Resource Division | 45.73 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000453/2024-2025 | 574/BSD | 10/09/2024 | 30/09/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.24 | 1.2 | 37.15 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Nebadhui Duttapukur (Zone - I) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 1712/BD | 08/06/2023 | 08/06/2025 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 386.46 | 181.58 | 46.99 | 75
6 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 24.19 | 0.11 | 11
Total | [13 empty] | 21806.27 | 206.98 | 0.95