## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1674/BD | 06/06/2023 | 06/06/2023 | Resource Division | 14.7 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 4373/BD | 10/11/2023 | 10/11/2023 | Resource Division | 16.37 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1280/BD | 25/04/2023 | 25/04/2023 | Resource Division | 45.73 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000453/2024-2025 | 574/BSD | 10/09/2024 | 30/09/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.24 | 1.2 | 37.15 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Nebadhui Duttapukur (Zone - I) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 1712/BD | 08/06/2023 | 08/06/2025 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 386.46 | 181.58 | 46.99 | 75
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (3rd Tubewell -Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000458/2024-2025 | 577/BSD | 10/09/2024 | 30/09/2024 | ROMI TREDERS. | 3.09 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (1st Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000456/2024-2025 | 575/BSD | 10/09/2024 | 30/09/2024 | M/S DAS & CO. | 3.26 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000457/2024-2025 | 576/BSD | 10/09/2024 | 30/09/2024 | M/S SANKAR ENTERPRISE. | 4.64 | 0 | 0 | 100
Total | [13 empty] | 477.5 | 182.79 | 38.28