## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1672/BD | 06/06/2023 | 06/06/2023 | Resource Division | 15.2 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1283/BD | 25/04/2023 | 25/04/2023 | Resource Division | 36.84 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Preparation of DPR in connection of augumentation of Shibalaya Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2022-2023 | 667/BSD | 25/08/2022 | 24/09/2022 | RADIANT | 3.07 | 2.79 | 91.14 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (1st Tubewell site - Pump House). | Assistant Engineer | Junior Engineer | ORD/000460/2024-2025 | 579/BSD | 10/09/2024 | 30/09/2024 | RANA ENTERPRISE | 2.66 | 1.69 | 63.58 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Arrangement of Block Level Orientation Programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks (Barasat-I & II) in North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000246/2024-2025 | 171/BSD | 10/06/2024 | 17/06/2024 | IMAGIN | 0.98 | 0.98 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Shibalaya water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000148/2023-2024 | 1713/BD | 08/06/2023 | 08/06/2025 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 364.71 | 185.68 | 50.91 | 80
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (2nd Tubewell site - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000461/2024-2025 | 580/BSD | 10/09/2024 | 30/09/2024 | B. S. ENTERPRISE (BANAMALIPUR) | 2.77 | 1.41 | 50.86 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (1st Tubewell site - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000459/2024-2025 | 578/BSD | 10/09/2024 | 30/09/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.2 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (2nd Tubewell site - Pump House). | Assistant Engineer | Junior Engineer | ORD/000463/2024-2025 | 581/BSD | 10/09/2024 | 30/09/2024 | M/S SUKANTA ENTERPRISE. | 2.65 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Shibalaya W/S Scheme (75.7 m3/hr) within Barasat-I Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000104/2024-2025 | 1924/BD | 09/07/2024 | 21/11/2024 | M/S SANKAR ENTERPRISE. | 7.44 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Fitting and fixing of sign Board (915mm x 610mm) for Demarcation of Land at Barasat-1 (14 nos.) Block under Barasat Sub Division under the Juridiction of Barasat Division, P.H.E. Dte. |  | Junior Engineer | ORD/000463/2025-2026 | 196/BSD | 02/06/2025 | 08/06/2025 | BIBHAS PAL. | 0.9 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | SM/13472 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47.4 | 0.22 | 11
Total | [13 empty] | 21780.18 | 239.95 | 1.1