## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002699/2021-2022 | 241/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.63 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Material Requisition To Resource Division |  |  | RTOR000223/2022-2023 | 874/BD | 22/03/2023 | 22/03/2023 | Resource Division | 15.62 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Sinking of 1 Nos. 300.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Atpukur w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2023-2024 | 1132/HSD | 05/09/2023 | 05/10/2023 | SARKAR ENTERPRISE & CO. | 2.63 | 0 | 0 | 100
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-A). | Assistant Engineer | Junior Engineer | ORD/001908/2023-2024 | 280/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.87 | 0 | 0 | 100
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-B). | Assistant Engineer | Junior Engineer | ORD/001909/2023-2024 | 281/HSD | 06/03/2024 | 16/03/2024 | S.M.TRADERS. | 0.88 | 0 | 0 | 100
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-D). | Assistant Engineer | Junior Engineer | ORD/001912/2023-2024 | 284/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0 | 0 | 100
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-J). | Assistant Engineer | Junior Engineer | ORD/001920/2023-2024 | 292/HSD | 06/03/2024 | 16/03/2024 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-E). | Assistant Engineer | Junior Engineer | ORD/001914/2023-2024 | 286/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0 | 0 | 100
9 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-C). | Assistant Engineer | Junior Engineer | ORD/001936/2023-2024 | 260/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0 | 0 | 100
10 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-H). | Assistant Engineer | Junior Engineer | ORD/001918/2023-2024 | 290/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.87 | 0 | 0 | 100
11 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Quotation for Service Connection Charges for PH- III, Zone-II under Atpukur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05524/2023-2024 | BP-355-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.56 | 0 | 0 | 0
12 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Quotation for Service Connection Charges for PH- I, Zone-II under Atpukur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05523/2023-2024 | BP-354-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.09 | 0 | 0 | 0
13 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Quotation for Service Connection Charges for PH- II, Zone-II under Atpukur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05548/2023-2024 | BP-356-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.5 | 0 | 0 | 0
14 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
15 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials and Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Atpukur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 1550/BD | 22/05/2023 | 21/03/2025 | SARKAR ENTERPRISE & CO. | 210.66 | 0 | 0 | 95
16 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme | SM/13510 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Atpukur water supply scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001466/2024-2025 | 341/HSD | 06/02/2025 | 16/02/2025 | RATAN SARKAR. | 0.72 | 0 | 0 | 100
Total | [13 empty] | 21601.31 | 0 | 0