## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (SANKARDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002732/2021-2022 | 308/HSD | 15/02/2022 | 02/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (SANKARDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002733/2021-2022 | 309/HSD | 15/02/2022 | 02/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.06 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Acceptance cum work order for Strengthing of Brick pavement road for movement of rig machineries for sinking of big dia Tube well at PH No-2 within Sankardaha w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000887/2023-2024 | 1129/HSD | 05/09/2023 | 12/09/2023 | RUDRA DAS. | 3.55 | 0 | 0 | 100
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Material Requisition To Resource Division |  |  | RTOR000215/2022-2023 | 884/BD | 22/03/2023 | 22/03/2023 | Resource Division | 17.11 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Sankardaha Piped water supply scheme | SM/13518 | New | New service connection for Sankardaha PH-I Sankardaha Minakhan |  |  | BILL/04044/2023-2024 | BP-254-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.58 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Sankardaha Piped water supply scheme | SM/13518 | New | New service connection for Sankardaha PH-II Sankardaha Minakhan |  |  | BILL/04045/2023-2024 | BP-255-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Acceptance cum work order for Strengthing of existing concrete & Brick pavement road for movement of rig machineries for sinking of big dia Tube well at PH No-1 within Sankardaha w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000906/2023-2024 | 2717/BD | 05/09/2023 | 12/09/2023 | ARBINA ENTERPRISE. | 5.56 | 0 | 0 | 100
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Acceptance cum work order for Emergent restoration of road for damage portion at different places in connection with retrofitting of Khas Sankardaha & Sankardaha Abad within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000553/2024-2025 | 995/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.93 | 0 | 0 | 100
9 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Sankardaha Piped water supply scheme | SM/13518 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Sankardaha water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001471/2024-2025 | 345/HSD | 06/02/2025 | 16/02/2025 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 100
11 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Sankardaha Piped water supply scheme | SM/13518 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Sankardaha W/S scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2023-2024 | 1699/BD | 08/06/2023 | 09/06/2025 | M/S DATTA ENTERPRISE. | 405.52 | 0 | 0 | 100
Total | [13 empty] | 21790.2 | 0 | 0