## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIBARIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002719/2021-2022 | 282/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIBARIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B). | Assistant Engineer | Junior Engineer | ORD/002720/2021-2022 | 283/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.49 | 2.49 | 100 | 0
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Material Requisition To Resource Division |  |  | RTOR000217/2022-2023 | 896/BD | 22/03/2023 | 22/03/2023 | Resource Division | 18.77 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Khariberia w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2023-2024 | 1705/BD | 08/06/2023 | 07/06/2026 | M/S PROGATI ENTERPRISE. | 400.07 | 272.17 | 68.03 | 90
5 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Service connection charges at PH-I under Khariberia W/S Scheme |  |  | BILL/04758/2023-2024 | BP-294-23-24 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 25.56 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Bamanpukuria & Khariberia w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001500/2024-2025 | 635/BD | 28/02/2025 | 14/04/2025 | ACME CONSTRUCTION | 51.71 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kharibaria Piped Water Supply Scheme. | SM/13519 | New | Formal work order for Additional Laying of UPVC distribution pipe line with Protection works in Sankardaha, Khariberia, Bargan Gopalpur & Mallickgheri mouzas under Khariberia w/s scheme within Minakhan block, Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000006/2025-2026 | 1798/BD | 30/05/2025 | 29/06/2025 | ATCO ENTERPRISE | 118.72 | 0 | 0 | 0
Total | [13 empty] | 622.14 | 279.49 | 44.92