## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/13521 | Retrofitting | Formal work order for Construction of 2 nos. (1250 CuM & 600 CuM) capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-X and XI Head work sites including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001211/2023-2024 | 4072/BD | 16/10/2023 | 15/10/2026 | GARGO TRADERS | 3804.4 | 390.88 | 10.27 | 44
Total | [13 empty] | 3804.4 | 390.88 | 10.27