## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002717/2021-2022 | 280/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.5 | 4.5 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002995/2021-2022 | 280/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.5 | 0 | 0 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Acceptance cum work order for Sinking of 1 Nos. 300.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Kachurhula w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001105/2023-2024 | 1190/HSD | 22/09/2023 | 02/10/2023 | ROY CHOWDHURY CONSTRUCTION. | 2.63 | 1.76 | 66.93 | 100
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Material Requisition To Resource Division |  |  | RTOR000210/2022-2023 | 892/BD | 22/03/2023 | 22/03/2023 | Resource Division | 17.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-H). | Assistant Engineer | Junior Engineer | ORD/001942/2023-2024 | 273/HSD | 06/03/2024 | 16/03/2024 | S.M.TRADERS. | 0.88 | 0.88 | 100 | 100
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Kachurhula w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 1693/BD | 07/06/2023 | 07/06/2025 | TRISHA ENTERPRISE & CO. | 166.1 | 72.97 | 43.93 | 16
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kachurhula w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001768/2023-2024 | 553/BD | 22/02/2024 | 01/07/2025 | SAHA CONSTRUCTION & CO | 33.41 | 0 | 0 | 50
8 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Quotation for 11 KV LT Bulk Connection at PH-II, zone-I of Kochurhula W/S scheme |  |  | BILL/02455/2024-2025 | BP-215 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.21 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Quotation for 11 KV LT Bulk Connection at PH-I, zone-I of Kochurhula W/S scheme |  |  | BILL/02400/2024-2025 | BP-216 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.04 | 0 | 0 | 0
10 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Kachurhula Zone-I Piped Water Supply Scheme | SM/13522 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 76.39 | 0.36 | 11
Total | [13 empty] | 21588.69 | 156.5 | 0.72