## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DEBITALA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002710/2021-2022 | 273/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.48 | 2.48 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DEBITALA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002709/2021-2022 | 272/HSD | 09/02/2022 | 24/02/2022 | UMWELT ENGINEER PVT.LTD. | 4.82 | 4.82 | 100 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BARGAN GOPALPUR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002705/2021-2022 | 248/HSD | 03/02/2022 | 18/02/2022 | UMWELT ENGINEER PVT.LTD. | 3.2 | 3.2 | 100 | 1
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Material Requisition To Resource Division |  |  | RTOR000212/2022-2023 | 895/BD | 22/03/2023 | 22/03/2023 | Resource Division | 27.76 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Debitala Piped Water Supply Scheme | SM/13523 | New | Quotation for Service Connection Charges for PH- II under Debitala W/S Scheme in the district of North 24 Pgs. |  |  | BILL/01392/2024-2025 | BP-85-24-25 | 09/08/2024 | 09/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.47 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Debitala Piped Water Supply Scheme | SM/13523 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 40.1 | 0.19 | 11
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Debitala w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2023-2024 | 1703/BD | 08/06/2023 | 05/12/2025 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 399.18 | 306.61 | 76.81 | 86
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Formal work order for Protection of different dia. UPVC pipeline by UC bullah & Bamboo pile at diff. places and emergent restoration of road at HW site in Debitala w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001034/2024-2025 | 3624/BD | 20/12/2024 | 18/06/2025 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 147.18 | 0 | 0 | 85
9 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Debitala Piped Water Supply Scheme | SM/13523 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Debitala water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/001883/2024-2025 | 528/HSD | 10/03/2025 | 20/03/2025 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 0
Total | [13 empty] | 21930.58 | 357.22 | 1.63