## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (CHUTKIA RADHANAGAR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002708/2021-2022 | 271/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.85 | 0.85 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (CHUTKIA RADHANAGAR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002706/2021-2022 | 249/HSD | 03/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 0
3 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Material Requisition To Resource Division |  |  | RTOR000213/2022-2023 | 883/BD | 22/03/2023 | 22/03/2023 | Resource Division | 28.59 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Eastern Mechanical | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | New service connection for Chutkia PH-I, Chutkia sankardaha |  |  | BILL/04050/2023-2024 | BP-250-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.17 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Eastern Mechanical | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | New service connection for Chutkia PH-II, Chutkia Sankardaha |  |  | BILL/04049/2023-2024 | BP-251-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Acceptance cum work order for Strengthing of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No- 2 within Chutkia Radhanagar w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000886/2023-2024 | 1128/HSD | 05/09/2023 | 12/09/2023 | NURJAHAN ENTERPRISE. | 1.69 | 1.51 | 89.54 | 100
7 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Central Drilling | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.6 | 0.26 | 11
8 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection at Chikar more end within Chutkia Radhanagar w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001536/2024-2025 | 111/BD | 09/01/2025 | 08/06/2025 | TARUN KUMAR LAHA | 7.47 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Minakhan,Sandeshkhali-I | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme | SM/13524 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Chutkia Radhanagar w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000039/2023-2024 | 1439/BD | 11/05/2023 | 02/04/2025 | R.K.MANDAL & CO. | 290.05 | 222.19 | 76.6 | 100
Total | [13 empty] | 21684.25 | 284.98 | 1.31