## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (HATBHANGA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002714/2021-2022 | 277/HSD | 09/02/2022 | 24/02/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 0.8 | 0.8 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (HATBHANGA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002713/2021-2022 | 276/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | Material Requisition To Resource Division |  |  | RTOR000225/2022-2023 | 880/BD | 22/03/2023 | 22/03/2023 | Resource Division | 16.26 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | New service connection for Hatbhanga PH-II, Hatbhanga minakhan |  |  | BILL/04048/2023-2024 | BP-252-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.76 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR, pipe connection and cost of pipes specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at P.H. No.-1 (Size - 5.40 x 3.60 mtr.) & P.H. No-2 (Size - 3.60 x 3.00 mtr.) for Hatbhanga W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 1714/BD | 08/06/2023 | 08/06/2024 | POWER TOOLS & ENGINEERING | 268.27 | 113.97 | 42.48 | 65
6 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | Quotation for Service Connection Charges for PH- I under Hathbhanga W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05542/2023-2024 | BP-357-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.74 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Hatbhanga Piped Water Supply Scheme | SM/13525 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21647.42 | 119.59 | 0.55