## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas D | SM/13534 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXIV) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001172/2023-2024 | 2959/BD | 29/09/2023 | 17/12/2025 | M/S S.S.ENTERPRISE. (SOUTH) | 1776.28 | 113.88 | 6.41 | 33
Total | [13 empty] | 1776.28 | 113.88 | 6.41