## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje | SM/13535 | Retrofitting | Formal work order for Laying of Distribution System, Providing FHTC, Construction of Office cum Guard room, Land development and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XX) i.e. Matikumra / (Zone-XXII) i.e. Chikanpara under Habra-Gaighata surface based PWSS, of Gaighata Block under Barasat Division, P.H.E. Dte. GAIGHATA BLOCK, PART-B / Gaighata Block, PART-D | Assistant Engineer | Junior Engineer | ORD/001214/2023-2024 | 4073/BD | 16/10/2023 | 15/10/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2790.09 | 0 | 0 | 88
Total | [13 empty] | 2790.09 | 0 | 0