## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | SM/13546 | Retrofitting | Formal work order for construction of 5 nos. different capacity OHR, Land development, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at different Zonal Head work site including Laying Distribution System and FHTC of surface based water supply scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2023-2024 | 2714/BD | 05/09/2023 | 04/09/2026 | S & P ENTERPRISE | 5112.52 | 0 | 0 | 40
Total | [13 empty] | 5112.52 | 0 | 0