## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Bithari Zone-I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002963/2021-2022 | 450/BHT | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Bithari Zone-I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002964/2021-2022 | 451/BHT | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.22 | 1.22 | 100 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Additional Survey work for DPR Preparation for BITHARI ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002507/2021-2022 | 451 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.22 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1241/BD | 25/04/2023 | 25/04/2023 | Resource Division | 145.39 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1631/BD | 01/06/2023 | 01/06/2023 | Resource Division | 43.69 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Zone-I water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 1357/BD | 04/05/2023 | 27/06/2025 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 723.95 | 376.45 | 52 | 48
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03470/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 39.73 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Bithari (Zone-I) W/S Scheme and Pump House No-I under Taranipur (Zone-I) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001889/2023-2024 | 6752/EMD | 28/11/2023 | 01/04/2025 | M.S. ENTERPRISE | 65.12 | 0 | 0 | 60
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Acceptance cum work order for special repair renovation of existing structures like Pump house, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Akhipur, Baro Bankra, Bithari Z-I, Bithari Z-II water supply scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000265/2025-2026 | 2381/BD | 10/07/2025 | 07/12/2025 | JP CONSTRUCTION & SUPPLIERS. | 81.91 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | SM/13737 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Swarupnagar Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - A) | Assistant Engineer | Junior Engineer | ORD/001491/2024-2025 | 152/BHTSD | 29/01/2025 | 18/02/2025 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
Total | [13 empty] | 1108.05 | 382.62 | 34.53