## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000236/2022-2023 | 926/BD | 22/03/2023 | 22/03/2023 | Resource Division | 4.71 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Formal work order for Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials and Laying of DI rising main, DI/UPVC distribution pipe line, providing Functional Household Tap Connection in connection with Augmentation of Chaimalpur water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 1221/BD | 20/04/2023 | 20/04/2024 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 215.47 | 205.22 | 95.25 | 65
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300 mm dia 48 mtr. long housing pipe & 200 mm dia 30 mtr. long filter for Augmentation of Chaimalpur w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000744/2023-2024 | 2496/BD | 21/08/2023 | 20/09/2023 | ANJALI ENTERPRISE. | 26.02 | 18.61 | 71.53 | 69
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Chhaimalpur W/S Scheme and Pump House No.I & II under Asharia-Narayanpur W/S Scheme , District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.-07) | Assistant Engineer | Junior Engineer | ORD/001672/2022-2023 | 1003/EMD | 09/03/2023 | 01/02/2025 | SWAPAN KUMAR BHANJA | 42.29 | 35.1 | 83.01 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Nandanpur mouza within Chaimalpur w/s scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001372/2024-2025 | 239/HSD | 30/01/2025 | 09/02/2025 | ABDUL HAMID GAZI. | 0.89 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Sirajpur mouza within Chaimalpur w/s scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001897/2024-2025 | 536/HSD | 10/03/2025 | 20/03/2025 | SARKAR ENTERPRISE | 0.97 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur | SM/13767 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Chaimalpur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000125/2025-2026 | 949/HSD | 29/05/2025 | 08/06/2025 | SARKAR ENTERPRISE | 0.93 | 0 | 0 | 100
Total | [13 empty] | 291.28 | 258.94 | 88.9