## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MALLIKGHERI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002724/2021-2022 | 289/HSD | 10/02/2022 | 25/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.81 | 2.81 | 100 | 0
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MALLIKGHERI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002727/2021-2022 | 288/HSD | 10/02/2022 | 25/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Material Requisition To Resource Division |  |  | RTOR000216/2022-2023 | 894/BD | 22/03/2023 | 22/03/2023 | Resource Division | 33.53 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Quotation for Service Connection Charges for PH- II under Mallickgheri W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05521/2023-2024 | BP-358-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.54 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Quotation for Service Connection Charges for PH- III under Mallickgheri W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05522/2023-2024 | BP-359-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 88.82 | 0.42 | 11
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Mallick Gheri W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000765/2023-2024 | 2579/BD | 25/08/2023 | 25/08/2026 | M/S DATTA ENTERPRISE. | 500.78 | 274.68 | 54.85 | 75
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Acceptance cum work order for 1 no. pump connection at PH No.-3 in connection within Mallickgheri water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/000115/2025-2026 | 942/HSD | 29/05/2025 | 08/06/2025 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Mallik Gheri Piped Water Supply Scheme. | SM/13813 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Mallickgheri water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/000149/2025-2026 | 998/HSD | 04/06/2025 | 14/06/2025 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 0
Total | [13 empty] | 21894.72 | 371.14 | 1.7