## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BAMANPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002703/2021-2022 | 246/HSD | 03/02/2022 | 18/02/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.99 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BAMANPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002704/2021-2022 | 245/HSD | 03/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 0 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Material Requisition To Resource Division |  |  | RTOR000205/2022-2023 | 887/BD | 22/03/2023 | 22/03/2023 | Resource Division | 17.54 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 1 no Block (Minakhan) in North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2024-2025 | 756/HSD | 19/07/2024 | 29/07/2024 | IMAGIN | 0.49 | 0 | 0 | 100
5 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at P.H. No.-1 (Size-5.40 x 3.60 mtr.) & P.H. No.-2 (Size-3.60 x 3.00 mtr.) for Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000146/2023-2024 | 1706/BD | 08/06/2023 | 08/06/2026 | MONDAL & CO. (BASIRHAT). | 462.55 | 0 | 0 | 86
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000416/2024-2025 | 2736/BD | 20/09/2024 | 17/07/2025 | M.R.CONSTRUCTION. | 130.43 | 0 | 0 | 70
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bamanpukuria Piped Water Supply Scheme. | SM/13814 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Bamanpukuria & Khariberia w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001500/2024-2025 | 635/BD | 28/02/2025 | 14/04/2025 | ACME CONSTRUCTION | 51.71 | 0 | 0 | 0
Total | [13 empty] | 22011.29 | 0 | 0