## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Uchildaha Piped water supply scheme | SM/13815 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (UCHILDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002736/2021-2022 | 312/HSD | 15/02/2022 | 02/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Uchildaha Piped water supply scheme | SM/13815 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (UCHILDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002737/2021-2022 | 313/HSD | 15/02/2022 | 02/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.89 | 3.89 | 100 | 0
3 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Uchildaha Piped water supply scheme | SM/13815 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 17.36 | 0.08 | 11
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Uchildaha Piped water supply scheme | SM/13815 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Uchildaha W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000766/2023-2024 | 2581/BD | 25/08/2023 | 25/08/2025 | MONDAL & CO. (BASIRHAT). | 488.99 | 384.77 | 78.69 | 75
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Uchildaha Piped water supply scheme | SM/13815 | New | Material Requisition To Resource Division |  |  | RTOR000222/2022-2023 | 877/BD | 22/03/2023 | 22/03/2023 | Resource Division | 30.59 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Uchildaha Piped water supply scheme | SM/13815 | New | Quotation for Service Connection Charges for PH- I under Uchildaha W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05534/2023-2024 | BP-360-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.22 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Uchildaha Piped water supply scheme | SM/13815 | New | Quotation for Service Connection Charges for PH- II under Uchildaha W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05545/2023-2024 | BP-361-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.78 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Uchildaha Piped water supply scheme | SM/13815 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Atpukur (Z-I) and Uchildaha w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001497/2024-2025 | 633/BD | 28/02/2025 | 14/04/2025 | SHIBU BISWAS. | 51.76 | 0 | 0 | 0
Total | [13 empty] | 21946.82 | 410.84 | 1.87