## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-V under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2022-2023 | 673/BSD | 31/08/2022 | 30/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.61 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 3089/BD | 10/10/2023 | 10/10/2023 | Resource Division | 21.99 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1288/BD | 25/04/2023 | 25/04/2023 | Resource Division | 48.13 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 4366/BD | 10/11/2023 | 10/11/2023 | Resource Division | 38.51 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Berachampa Zone - V 1st Tubewell site at Kaukepara Mouza within Deganga Block under Barasat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001041/2024-2025 | 3702/BD | 26/12/2024 | 25/01/2025 | DEBAPRASAD MONDAL. | 27.57 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tubewell by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-V Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001927/2023-2024 | 804/BD | 12/03/2024 | 11/04/2024 | ACME CONSTRUCTION | 13.08 | 12.47 | 95.34 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-V water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002154/2023-2024 | 1245/BSD | 15/03/2024 | 15/04/2024 | SANTU GHOSH. | 4.91 | 4.9 | 99.77 | 90
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | New service connection at P.H.No- I Zone- V of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04804/2023-2024 | BP-304-23-24 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.99 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Additional quotation for New service connection at P.H.No- I , Zone- V of Berachampa water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) |  |  | BILL/05840/2023-2024 | BP-11-24-25 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | SM/13892 | Augmentation | Formal work order for Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Berachampa Zone-V Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2023-2024 | 4070/BD | 16/10/2023 | 02/09/2025 | DEBAPRASAD MONDAL. | 567.01 | 187.89 | 33.14 | 45
Total | [13 empty] | 729 | 208.87 | 28.65