## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Repairing & Renovation of 1 No. Pump House (P.H. No-IV) and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002945/2021-2022 | 832/BSD | 16/12/2021 | 15/01/2022 | ROMI TREDERS. | 1.25 | 1.18 | 94.55 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002954/2021-2022 | 830/BSD | 16/12/2021 | 15/01/2022 | P.ENTERPRISE. | 1.85 | 1.75 | 94.66 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-II & III) and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002953/2021-2022 | 831/BSD | 16/12/2021 | 15/01/2022 | KABASI ENTERPRISE. | 2.51 | 2.39 | 95.15 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 659/BSD | 18/08/2022 | 17/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.58 | 99.37 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 3087/BD | 10/10/2023 | 10/10/2023 | Resource Division | 18.46 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1269/BD | 25/04/2023 | 25/04/2023 | Resource Division | 32.07 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-D | Assistant Engineer | Junior Engineer | ORD/001844/2023-2024 | 1119/1/BSD | 09/02/2024 | 13/02/2024 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Arrangement of Block Level Orientation Programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks (Amdanga & Deganga) in North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000247/2024-2025 | 172/BSD | 10/06/2024 | 17/06/2024 | IMAGIN | 0.98 | 0.98 | 100 | 100
9 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Formal work order for Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Berachampa Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000564/2023-2024 | 2447/BD | 16/08/2023 | 01/04/2026 | H.I.ENTERPRISE. | 556.61 | 346.11 | 62.18 | 78
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I, II and IV) under Berachampa W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000823/2022-2023 | 30/EMDdt.03.01.2023 | 10/02/2023 | 01/07/2025 | M/S P.P. ELECTRICALS | 78.21 | 0 | 0 | 66
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Berachampa Zone-II Water Supply Scheme within Deganga Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001155/2024-2025 | 615/BD | 27/02/2025 | 08/04/2025 | ANJALI ENTERPRISE. | 9.21 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | SM/13893 | Augmentation | Acceptance cum work order for Sinking of 3 nos 300mm. X 200mm.dia. 200.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long UPVC Medium Well Screen (RMS) Pipes with Ribs at Berachampa Zone-II( H/W site & 2nd T/W site) & Berachampa Zone-III( 2nd T/W site) Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001503/2024-2025 | 646/BD | 28/02/2025 | 29/04/2025 | JOY GURU ENTERPRISE | 42.76 | 0 | 0 | 0
Total | [13 empty] | 22088.16 | 356.88 | 1.62