## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Bongaon | Barasat Division | Garibpur Piped water supply scheme | SM/13897 | New | Survey, Design, Drawing & DPR preparation for new PWSS at Garibpur water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000852/2022-2023 | 348/Bon | 07/07/2022 | 28/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.45 | 4.45 | 100 | 1
2 | NORTH 24 PARGANAS | Bongaon | Barasat Division | Garibpur Piped water supply scheme | SM/13897 | New | Formal Work order for Construction of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Garibpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme) | Assistant Engineer | Junior Engineer | ORD/000248/2023-2024 | 2057/BD | 14/07/2023 | 14/07/2026 | AMIT KUMAR BOSE. | 223.93 | 116.43 | 51.99 | 54
3 | NORTH 24 PARGANAS | Bongaon | Eastern Mechanical | Garibpur Piped water supply scheme | SM/13897 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. Garibpur W/S Scheme (P/H -I) District of 24 Pgs. (N). N.I.E.T No. 29 of EE / EMD of 2022-2023 (2022_PHED_434059_36) | Assistant Engineer | Junior Engineer | ORD/001887/2023-2024 | 6732/EMD | 28/11/2023 | 01/07/2025 | A.G ENTERPRISE. | 10.11 | 0 | 0 | 90
4 | NORTH 24 PARGANAS | Bongaon | Barasat Division | Garibpur Piped water supply scheme | SM/13897 | New | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Garibpur Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001015/2023-2024 | 2832/BD | 15/09/2023 | 15/10/2023 | NADIA TUBEWELLS | 21.56 | 15.59 | 72.31 | 100
5 | NORTH 24 PARGANAS | Bongaon | Barasat Division | Garibpur Piped water supply scheme | SM/13897 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1866/BD | 23/06/2023 | 23/06/2023 | Resource Division | 4.65 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Bongaon | Barasat Division | Garibpur Piped water supply scheme | SM/13897 | New | Acceptance cum work order for Construction of Boundary wall, Approach Road and Land development at Head Work site of Garibpur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000572/2024-2025 | 3157/BD | 14/11/2024 | 14/12/2024 | AMIT KUMAR BOSE. | 34.19 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Bongaon | Barasat Division | Garibpur Piped water supply scheme | SM/13897 | New | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Garibpur w/s scheme Bongaon Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002173/2023-2024 | 607/BD | 23/02/2024 | 26/12/2024 | TAPAN GHOSH. | 5.61 | 1.49 | 26.48 | 100
8 | NORTH 24 PARGANAS | Bongaon | Eastern Mechanical | Garibpur Piped water supply scheme | SM/13897 | New | New service connection at P.H.No- I of Garibpur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/04883/2023-2024 | BP-328-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.5 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Bongaon | Eastern Mechanical | Garibpur Piped water supply scheme | SM/13897 | New | Additional quotation for New service connection at P.H.No- I of Garibpur water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/02437/2024-2025 | BP-218 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.28 | 0 | 0 | 0
Total | [13 empty] | 314.29 | 137.95 | 43.89