## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 2093/BD | 18/07/2023 | 18/07/2023 | Resource Division | 12.63 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1862/BD | 23/06/2023 | 23/06/2023 | Resource Division | 12.63 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002518/2023-2024 | 87/Bon | 30/01/2024 | 30/07/2024 | ROY ENGINEERS. | 0.86 | 1.8 | 208.2 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002530/2023-2024 | 484/Bon | 30/06/2023 | 31/12/2023 | VAI ENTERPRISE. | 0.87 | 1.78 | 203.61 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota(Additional) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 2030/BD | 13/07/2023 | 11/10/2023 | RAJ KUMAR MONDAL | 175.4 | 174.09 | 99.25 | 70
6 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 2928/BD | 26/09/2023 | 26/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 5.21 | 32.29 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household of Kundipur, Kundipur Jalkar and Keutipara mouza including laying of UPVC pipe under Augmentation work at additional Gangrapota & Gangrapota W/S Scheme, Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000019/2025-2026 | 1650/BD | 21/05/2025 | 19/08/2025 | REAL TIME | 43.26 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | SM/13984 | Augmentation | Acceptance cum work order for Repairing and renovation works for 450 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Gangrapota Water Supply Scheme,Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000020/2024-2025 | 1537/BD | 07/06/2024 | 04/03/2025 | MONDAL ENTERPRISE. (BARASAT) | 18.37 | 0 | 0 | 100
Total | [13 empty] | 280.14 | 182.86 | 65.28