## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1274/BD | 25/04/2023 | 25/04/2023 | Resource Division | 23.58 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1675/BD | 06/06/2023 | 06/06/2023 | Resource Division | 7.07 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Donnagar W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001146/2023-2024 | 4749/EMD | 07/08/2023 | 06/09/2023 | BARISAL TRADING CO. | 20.19 | 0 | 0 | 85
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | Augmentation | Acceptance cum work order for Sinking of 250mm. X 150mm.dia. 300.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 30.0mtr. long PVC housing pipe & 150mm.dia. 30.0mtr. long pre-packed resin bonded filter at Head Work Site of Donnagar Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000830/2022-2023 | 523/BD | 20/02/2023 | 07/03/2023 | M/S SUKANTA ENTERPRISE. | 14.69 | 0 | 0 | 32
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | Augmentation | Preparation of DPR in connection of augumentation of Donnagar Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-15 | Assistant Engineer | Junior Engineer | ORD/000308/2022-2023 | 562/BSD | 29/06/2022 | 29/07/2022 | RADIANT | 2.6 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | SM/14127 | Augmentation | Formal work order for Laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Donnagar Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2023-2024 | 1531/BD | 19/05/2023 | 30/03/2025 | M/S S. & P CONSTRUCTION | 147.04 | 0 | 0 | 20
Total | [13 empty] | 215.16 | 0 | 0