## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2022-2023 | 794/BD | 13/03/2023 | 12/04/2023 | M/S RAJPATH CONSTRUCTION. | 42.87 | 33.12 | 77.26 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2022-2023 | 401/BD | 09/02/2023 | 10/05/2023 | M/S PROGATI ENTERPRISE. | 306.25 | 293.07 | 95.7 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001121/2022-2023 | 404/BD | 09/02/2023 | 10/05/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 283.51 | 257.49 | 90.82 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001174/2022-2023 | 787/BD | 13/03/2023 | 12/04/2023 | M/S RAJPATH CONSTRUCTION. | 21.45 | 14.51 | 67.66 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000720/2023-2024 | 2473/BD | 18/08/2023 | 17/09/2023 | ABDUL ALIM MONDAL. | 16.45 | 13.27 | 80.67 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000260/2022-2023 | 917/BD | 22/03/2023 | 22/03/2023 | Resource Division | 2.48 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I)(Rep.) and Pump House No- I and II (New) (Zone-II) under Mohanpur W/S Scheme in the District of 24 Pgs. (N) NIET No. 34 of EE/EMD of 2022-23 (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/001932/2022-2023 | 1231/EMD | 24/03/2023 | 23/04/2023 | ASHUTOSH DAS & CO. | 53 | 0 | 0 | 90
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Mohanpur water supply scheme (Zone-I), Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001263/2023-2024 | 4193/BD | 30/10/2023 | 29/10/2024 | M/S RAJPATH CONSTRUCTION. | 114.56 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Mohanpur Zone-II in connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000317/2024-2025 | 2275/BD | 12/08/2024 | 12/08/2025 | M/S B.K.ENTERPRISE. | 100.39 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 1441/BD | 11/05/2023 | 10/07/2023 | ROYAL CONSTRUCTION | 16.03 | 15.09 | 94.14 | 62
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Uttar Kalibari Adhikary House to PH No- 2 within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000279/2023-2024 | 806/HSD | 13/07/2023 | 20/07/2023 | SARKAR ENTERPRISE | 0.9 | 0.9 | 100.58 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for 2 no. pump connection at PH No.-1 & 2 in connection with Augmentation for Mohanpur water supply scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 868/HSD | 07/08/2024 | 14/08/2024 | ANKUSH CONSTRUCTION & CO. | 1.17 | 1.05 | 89.72 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI rising main from PH No-1 to Uttar Kalibari Adhikary House within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002499/2023-2024 | 803/HSD | 13/07/2023 | 20/07/2023 | SARKAR ENTERPRISE | 0.98 | 0.97 | 99.2 | 100
14 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Quotation for Service Connection Charges for PH- I, Zone-II under Mohanpur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/01395/2024-2025 | BP-84-24-25 | 09/08/2024 | 09/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.47 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Quotation for Service Connection Charges for PH- II, Zone-II under Mohanpur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05605/2023-2024 | BP-363-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
Total | [13 empty] | 973.51 | 629.46 | 64.66