## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2022-2023 | 794/BD | 13/03/2023 | 12/04/2023 | M/S RAJPATH CONSTRUCTION. | 42.87 | 33.12 | 77.26 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I)(Rep.) and Pump House No- I and II (New) (Zone-II) under Mohanpur W/S Scheme in the District of 24 Pgs. (N) NIET No. 34 of EE/EMD of 2022-23 (Sl. No. 08) | Assistant Engineer | Junior Engineer | ORD/001932/2022-2023 | 1231/EMD | 24/03/2023 | 23/04/2023 | ASHUTOSH DAS & CO. | 53 | 0 | 0 | 90
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Mohanpur water supply scheme (Zone-I), Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001263/2023-2024 | 4193/BD | 30/10/2023 | 29/10/2024 | M/S RAJPATH CONSTRUCTION. | 114.56 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2022-2023 | 401/BD | 09/02/2023 | 10/05/2023 | M/S PROGATI ENTERPRISE. | 306.25 | 293.07 | 95.7 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001121/2022-2023 | 404/BD | 09/02/2023 | 10/05/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 283.51 | 257.49 | 90.82 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 1441/BD | 11/05/2023 | 10/07/2023 | ROYAL CONSTRUCTION | 16.03 | 15.09 | 94.14 | 62
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001174/2022-2023 | 787/BD | 13/03/2023 | 12/04/2023 | M/S RAJPATH CONSTRUCTION. | 21.45 | 14.51 | 67.66 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000720/2023-2024 | 2473/BD | 18/08/2023 | 17/09/2023 | ABDUL ALIM MONDAL. | 16.45 | 13.27 | 80.67 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Uttar Kalibari Adhikary House to PH No- 2 within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000279/2023-2024 | 806/HSD | 13/07/2023 | 20/07/2023 | SARKAR ENTERPRISE | 0.9 | 0.9 | 100.58 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI rising main from PH No-1 to Uttar Kalibari Adhikary House within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002499/2023-2024 | 803/HSD | 13/07/2023 | 20/07/2023 | SARKAR ENTERPRISE | 0.98 | 0.97 | 99.2 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000260/2022-2023 | 917/BD | 22/03/2023 | 22/03/2023 | Resource Division | 2.48 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Mohanpur Zone-II in connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000317/2024-2025 | 2275/BD | 12/08/2024 | 12/08/2025 | M/S B.K.ENTERPRISE. | 100.39 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for 2 no. pump connection at PH No.-1 & 2 in connection with Augmentation for Mohanpur water supply scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 868/HSD | 07/08/2024 | 14/08/2024 | ANKUSH CONSTRUCTION & CO. | 1.17 | 1.05 | 89.72 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for 2 no. pump connection at PH No.-1 & 2 in connection with Augmentation for Mohanpur water supply scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 867/HSD | 07/08/2024 | 14/08/2024 | SARKAR ENTERPRISE & CO. | 1.17 | 0 | 0 | 100
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Quotation for Service Connection Charges for PH- I, Zone-II under Mohanpur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/01395/2024-2025 | BP-84-24-25 | 09/08/2024 | 09/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.47 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Quotation for Service Connection Charges for PH- II, Zone-II under Mohanpur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05605/2023-2024 | BP-363-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Protection work by bamboo piling in different places in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 309/HSD | 04/02/2025 | 14/02/2025 | SARKAR ENTERPRISE | 0.94 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001430/2024-2025 | 310/HSD | 04/02/2025 | 14/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.81 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Protection work by bamboo piling in different places of Kalibari in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001511/2024-2025 | 375/HSD | 10/02/2025 | 20/02/2025 | SARKAR ENTERPRISE | 0.94 | 0 | 0 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Kalibari and Tangramari in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001509/2024-2025 | 373/HSD | 10/02/2025 | 20/02/2025 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001510/2024-2025 | 374/HSD | 10/02/2025 | 20/02/2025 | ANKUSH CONSTRUCTION & CO. | 0.32 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur | SM/14151 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001613/2024-2025 | 477/HSD | 28/02/2025 | 10/03/2025 | M/S RAJPATH CONSTRUCTION. | 0.81 | 0 | 0 | 100
Total | [13 empty] | 979.46 | 629.46 | 64.27