## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Radharani High School at Sandeshkhali in connection with augmentation of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000868/2023-2024 | 1054/HSD | 31/08/2023 | 07/09/2023 | M/S RAJPATH CONSTRUCTION. | 0.9 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000248/2022-2023 | 937/BD | 22/03/2023 | 22/03/2023 | Resource Division | 50.86 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 4174/BD | 30/10/2023 | 30/10/2023 | Resource Division | 10.35 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Dhamakhali mouza with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001026/2024-2025 | 3583/BD | 18/12/2024 | 17/01/2025 | TITUMIR INTERNATIONAL | 25.86 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002449/2023-2024 | 34/HSD | 09/01/2024 | 19/01/2024 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.23 to 31.10.23 = 61 days. | Assistant Engineer | Junior Engineer | ORD/002445/2023-2024 | 1030/HSD | 29/08/2023 | 29/10/2023 | SUSMITA MANDAL. | 0.91 | 2.66 | 293 | 5
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.11.23 to 30.04.24 | Assistant Engineer | Junior Engineer | ORD/002446/2023-2024 | 1396/HSD | 31/10/2023 | 30/04/2024 | RANJIT KUMAR MANDAL | 1.61 | 5.42 | 336.81 | 5
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Work order for Supply of one motor launch on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.11.23 to 31.03.24 = 152 days. | Assistant Engineer | Junior Engineer | ORD/002444/2023-2024 | 1362/HSD | 31/10/2023 | 31/03/2024 | SUSMITA MANDAL. | 2.26 | 7.48 | 330.17 | 10
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks ( Sandeshkhali- I & II ) in North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 755/HSD | 19/07/2024 | 29/07/2024 | IMAGIN | 0.98 | 0.98 | 100 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002429/2023-2024 | 33/HSD | 09/01/2024 | 19/01/2024 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line & providing Functional Household Tap Connection with other allied works for Augmentation of Sandeshkhali water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 1300/BD | 26/04/2023 | 13/10/2025 | KINGS & CO. | 356.31 | 144.22 | 40.48 | 45
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Sandeshkhali W/S Scheme , District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001263/2023-2024 | 4932/EMD | 18/08/2023 | 01/07/2025 | SWAPAN ENTERPRISE | 22.26 | 0 | 0 | 70
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001295/2024-2025 | 865/BD | 19/03/2025 | 12/06/2026 | M/S K.B.ENTERPRISE. | 102.2 | 0 | 0 | 30
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Additional Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection at Dhamakhali mouza within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001417/2024-2025 | 864/BD | 19/03/2025 | 30/10/2025 | RUDRA DAS. | 10.58 | 0 | 0 | 90
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Construction of 200 cum capacity CWR , pipe connection and cost of pipes, specials for Augmentation of Sandeshkhali water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000027/2025-2026 | 1499/BD | 13/05/2025 | 09/11/2025 | SUFIA ENTERPRISE | 53.52 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000729/2023-2024 | 2478/BD | 18/08/2023 | 08/02/2025 | M/S SUKANTA ENTERPRISE. | 31.71 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Additional Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection at Rampur & Jhupkhali adjoining mouza within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001418/2024-2025 | 863/BD | 19/03/2025 | 02/06/2025 | ABUL KALAM GAZI | 10.6 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method at PH No.-I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sandeshkhali W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001015/2024-2025 | 3581/BD | 18/12/2024 | 26/02/2025 | M/S SUKANTA ENTERPRISE. | 31.67 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali | SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001022/2024-2025 | 3578/BD | 18/12/2024 | 17/04/2025 | M/S RAJPATH CONSTRUCTION. | 31.66 | 0 | 0 | 100
Total | [13 empty] | 746.09 | 160.76 | 21.55