## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-I) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000216/2023-2024 | 1731/BD | 08/06/2023 | 02/06/2024 | M/S PROGATI ENTERPRISE. | 141.21 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Construction of 300 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-II) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2023-2024 | 1733/BD | 08/06/2023 | 07/06/2024 | M/S NIRMAN CONSTRUCTION. | 150.78 | 0 | 0 | 35
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III, IV & V under Kalitala W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001171/2023-2024 | 4799/EMD | 09/08/2023 | 09/03/2025 | ASHUTOSH DAS & CO. | 54.35 | 0 | 0 | 75
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-II , III, IV (Zone-II) under Kalitala ground water based water supply scheme under Block_ Hingalganj Dist. - 24Pgs(N) under EMD, PHE Dte. (SM/14153) | Assistant Engineer |  | ORD/000648/2024-2025 | 2685/EMD | 20/11/2024 | 20/12/2024 | R.N.S. TRADING | 36.65 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000565/2024-2025 | 1005/HSD | 29/08/2024 | 08/09/2024 | ABDUL ALIM MONDAL. | 0.99 | 0 | 0 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places from N/H/O Narayan Biswas to Naskar para culvert in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000567/2024-2025 | 1007/HSD | 29/08/2024 | 08/09/2024 | ABDUL ALIM MONDAL. | 0.99 | 0 | 0 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001148/2022-2023 | 654/BD | 28/02/2023 | 29/05/2023 | SUPRITI ENTERPRISE. | 610.1 | 522.73 | 85.68 | 60
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 1151/BD | 13/04/2023 | 12/07/2023 | UMWELT ENGINEER PVT.LTD. | 851.89 | 417.67 | 49.03 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000728/2023-2024 | 2477/BD | 18/08/2023 | 17/09/2023 | M/S PROGATI ENTERPRISE. | 63.27 | 0 | 0 | 71
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000726/2023-2024 | 2476/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 63.24 | 23.51 | 37.18 | 98
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001682/2023-2024 | 528/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 61.24 | 0 | 0 | 100
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001681/2023-2024 | 529/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 61.24 | 0 | 0 | 100
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000254/2022-2023 | 925/BD | 22/03/2023 |  | Resource Division | 280.28 | 0 | 0 | 0
14 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 4509/BD | 28/11/2023 |  | Resource Division | 17.23 | 0 | 0 | 0
Total | [13 empty] | 2393.46 | 963.91 | 40.27