## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000254/2022-2023 | 925/BD | 22/03/2023 | 22/03/2023 | Resource Division | 280.28 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 4509/BD | 28/11/2023 | 28/11/2023 | Resource Division | 17.23 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-II , III, IV (Zone-II) under Kalitala ground water based water supply scheme under Block_ Hingalganj Dist. - 24Pgs(N) under EMD, PHE Dte. (SM/14153) | Assistant Engineer | Junior Engineer | ORD/000648/2024-2025 | 2685/EMD | 20/11/2024 | 20/12/2024 | R.N.S. TRADING | 36.65 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001148/2022-2023 | 654/BD | 28/02/2023 | 29/05/2023 | SUPRITI ENTERPRISE. | 610.1 | 591.61 | 96.97 | 60
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 1151/BD | 13/04/2023 | 12/07/2023 | UMWELT ENGINEER PVT.LTD. | 851.89 | 839.63 | 98.56 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000728/2023-2024 | 2477/BD | 18/08/2023 | 17/09/2023 | M/S PROGATI ENTERPRISE. | 63.27 | 43.87 | 69.35 | 71
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000726/2023-2024 | 2476/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 63.24 | 47.03 | 74.37 | 98
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001682/2023-2024 | 528/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 61.24 | 45.07 | 73.6 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001681/2023-2024 | 529/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 61.24 | 46.06 | 75.22 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000565/2024-2025 | 1005/HSD | 29/08/2024 | 08/09/2024 | ABDUL ALIM MONDAL. | 0.99 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places from N/H/O Narayan Biswas to Naskar para culvert in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000567/2024-2025 | 1007/HSD | 29/08/2024 | 08/09/2024 | ABDUL ALIM MONDAL. | 0.99 | 0.52 | 53.08 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-I) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000216/2023-2024 | 1731/BD | 08/06/2023 | 08/06/2026 | M/S PROGATI ENTERPRISE. | 141.21 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Formal work order for Construction of 300 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-II) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2023-2024 | 1733/BD | 08/06/2023 | 07/06/2025 | M/S NIRMAN CONSTRUCTION. | 150.78 | 54.42 | 36.09 | 75
14 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III, IV & V under Kalitala W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001171/2023-2024 | 4799/EMD | 09/08/2023 | 09/03/2025 | ASHUTOSH DAS & CO. | 54.35 | 0 | 0 | 75
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Kalitala Bazar at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/000103/2025-2026 | 930/HSD | 29/05/2025 | 08/06/2025 | CHANCHAL ENTERPRISE & CO. | 0.82 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Retrofitting work at Samsernagar river side area in connection with Augmentation of Kalitala w/s scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001309/2024-2025 | 155/HSD | 27/01/2025 | 06/02/2025 | CHANCHAL ENTERPRISE & CO. | 0.98 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Withdrawing & relaying of 90 mm dia. UPVC pipe line near Paschim Kalitala in connection with Augmentation of Kalitala W/S Scheme, Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001310/2024-2025 | 156/HSD | 27/01/2025 | 06/02/2025 | CHANCHAL ENTERPRISE & CO. | 0.95 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Protection of newly restored UPVC distribution pipeline by Bamboo pilling at Hatkhola area in connection with augmentation of Kalitala w/s scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001311/2024-2025 | 157/HSD | 27/01/2025 | 06/02/2025 | CHANCHAL ENTERPRISE & CO. | 0.87 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Kamalakhali more at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001476/2024-2025 | 349/HSD | 06/02/2025 | 16/02/2025 | CHANCHAL ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at Duckbunglow at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001456/2024-2025 | 336/HSD | 06/02/2025 | 16/02/2025 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Laskar para at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001388/2024-2025 | 254/HSD | 30/01/2025 | 09/02/2025 | ABDUL ALIM MONDAL. | 0.97 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Construction of boundary wall at PH No.-8 & 9 for Augmentation of Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2024-2025 | 1527/BD | 07/06/2024 | 07/07/2024 | LAHIRI CONSTRUCTION. | 6.27 | 0 | 0 | 100
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at OHR site within Kalitala W/S scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001373/2024-2025 | 240/HSD | 30/01/2025 | 09/02/2025 | S.K.ENTERPRISE. | 0.97 | 0 | 0 | 100
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Protection work for construction of approach road for movement of winch machine and other allied machineries at OHR site within Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001374/2024-2025 | 241/HSD | 30/01/2025 | 09/02/2025 | M/S NIRMAN CONSTRUCTION. | 0.95 | 0 | 0 | 100
25 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Daspara more at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001887/2024-2025 | 530/HSD | 10/03/2025 | 20/03/2025 | CHANCHAL ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
26 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Ghosh para at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001378/2024-2025 | 245/HSD | 30/01/2025 | 09/02/2025 | ABDUL ALIM MONDAL. | 0.97 | 0 | 0 | 100
27 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | SM/14153 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Dakshin para at Parghumti mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001427/2024-2025 | 308/HSD | 04/02/2025 | 14/02/2025 | ABDUL ALIM MONDAL. | 0.98 | 0 | 0 | 100
Total | [13 empty] | 2411.02 | 1668.22 | 69.19