## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Rep.) under Chandrapur W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_13) |  |  | ORD/001885/2023-2024 | 6729/EMD | 28/11/2023 | 28/12/2023 | EASTERN INDIA SALES & SERVICE | 13.23 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 4022/BD | 12/10/2023 | 12/10/2023 | Resource Division | 55.3 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1276/BD | 25/04/2023 | 25/04/2023 | Resource Division | 208.17 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000430/2024-2025 | 562/BSD | 09/09/2024 | 29/09/2024 | JIBON BOSE. | 2.95 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (3rd Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000433/2024-2025 | 565/BSD | 09/09/2024 | 29/09/2024 | SUN ENTERPRISE. | 3.78 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 months from w.e.f. 01.12.2023) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001855/2023-2024 | 857/BSD | 29/11/2023 | 30/05/2024 | MADHAB CHANDRA DAS | 0.87 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Construction of New Pump House (Charkhara Mouza) with latrine at Chandrapur Water Supply Scheme under Barasat-I Block, size of 3.00m x 3.60m with latrine within Barasat Sub Division, P.H.E.Dte. |  | Junior Engineer | ORD/002150/2023-2024 | 1241/BSD | 15/03/2024 | 15/04/2024 | S.MUKHERJEE. | 4.18 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (1st Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000429/2024-2025 | 561/BSD | 09/09/2024 | 29/09/2024 | S.MUKHERJEE. | 4.1 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Preparation of DPR in connection of augumentation of Chandrapur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2022-2023 | 456/BSD | 20/05/2022 | 19/06/2022 | RADIANT | 4.58 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Construction of Culvert at Pump House - V of Chandrapur W/S Scheme under Barasat Sub. Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2024-2025 | 509/BSD | 30/08/2024 | 14/09/2024 | S.MUKHERJEE. | 0.86 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001851/2023-2024 | 1121/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Construction of New Pump House (Digha Mouza) with latrine at Chandrapur Water Supply Scheme under Barasat-I Block, size of 3.00m x 3.60m with latrine within Barasat Sub Division, P.H.E.Dte. |  | Junior Engineer | ORD/000030/2024-2025 | 166/BSD | 07/06/2024 | 07/07/2024 | JIBON BOSE. | 4.18 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | New service connection at P.H.No- III of Chandrapur water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04487/2023-2024 | BP-280-23-24 | 07/02/2024 | 07/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.49 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | New service connection at P.H.No- II of Chandrapur water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). |  |  | BILL/04486/2023-2024 | BP-279-23-24 | 07/02/2024 | 07/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.96 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
16 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.IV and V (New) under Chandrapur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001147/2023-2024 | 4750/EMD | 07/08/2023 | 01/04/2025 | D.K. ELECTRIC | 26.48 | 0 | 0 | 40
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Formal work order for Construction of 1200cum capacity 20mtr.Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and Providing FHTC for Augmentation of Chandrapur Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001189/2023-2024 | 3062/BD | 09/10/2023 | 01/08/2025 | MONDAL ENTERPRISE. (BARASAT) | 1459.09 | 0 | 0 | 46
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Chandrapur Water Supply Scheme under JJM programme in Barasat-I block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2024-2025 | 2004/BD | 18/07/2024 | 11/10/2025 | KINGS & CO. | 682.84 | 0 | 0 | 34
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | SM/14161 | Augmentation | Formal work order for road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-I and Amdanga Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2025-2026 | 1306/BD | 24/04/2025 | 22/08/2025 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 99.64 | 0 | 0 | 0
Total | [13 empty] | 23924.35 | 0 | 0