## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 3095/BD | 10/10/2023 | 10/10/2023 | Resource Division | 21.72 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1266/BD | 25/04/2023 | 25/04/2023 | Resource Division | 158.32 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.IV (Zone-II) (New) under Bodai W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001149/2023-2024 | 4752/EMD | 07/08/2023 | 06/09/2023 | SMILE | 13.14 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Formal work order for construction of 750 cum capacity 20 mtr. height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Bodai (Zone-II) water supply scheme under Barsasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000763/2023-2024 | 2617/BD | 29/08/2023 | 29/08/2026 | SUPRITI ENTERPRISE. | 874.9 | 144.08 | 16.47 | 20
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. Sl. No.-02 | Assistant Engineer | Junior Engineer | ORD/000288/2022-2023 | 549/BSD | 29/06/2022 | 29/07/2022 | RADIANT | 3.41 | 3.39 | 99.2 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-C | Assistant Engineer | Junior Engineer | ORD/001839/2023-2024 | 1116A/BSD | 09/02/2024 | 13/02/2024 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-II Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2024-2025 | 2229/BD | 07/08/2024 | 31/10/2025 | CHANDA CONSTRUCTION. | 433.82 | 0 | 0 | 25
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Different works in connection with Augmentation Bodai Zone-II PWSS (1st Tubewell - Pump House). |  | Junior Engineer | ORD/001099/2024-2025 | 1002/BSD | 02/01/2025 | 22/01/2025 | M/S DAS & CO. | 3.93 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Acceptance cum work order for for Construction of Pump House with latrine at Bodai Zone-II water Supply Scheme under Amdanga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002255/2023-2024 | 932/BD | 15/03/2024 | 14/06/2024 | M/S DAS & CO. | 5.09 | 4.9 | 96.46 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250mm. X 150mm.dia. 220.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 42.0mtr. long UPVC housing pipe & 150mm.dia. 30.0mtr. long filter for Augmentation of Bodai Zone-II Water Supply Scheme at 2nd Tubewell Site under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001029/2024-2025 | 3586/BD | 18/12/2024 | 18/03/2025 | M/S K.P.PAL. | 11.56 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Different works in connection with Augmentation Bodai Zone-II PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road) | Assistant Engineer | Junior Engineer | ORD/001106/2024-2025 | 1007/BSD | 02/01/2025 | 22/01/2025 | PURBA SERVICES | 1.93 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Differents works in connection with Augmentation Bodai Zone-II PWSS (3rd Tubewell - Pump House, Boundary Wall & Service Road) |  | Junior Engineer | ORD/001109/2024-2025 | 1008/BSD | 02/01/2025 | 22/01/2025 | M/S SOURAV DAS | 2.64 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Quotation for New service connection at P.H.No- OHR , Zone - II of Bodai water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/02720/2024-2025 | BP-249 | 16/03/2025 | 16/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 17.33 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 56.22 | 0.26 | 11
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | SM/14162 | Augmentation | Different works in connection with Augmentation Bodai Zone-II PWSS (1st Tubewell - Boundary Wall). |  | Junior Engineer | ORD/001101/2024-2025 | 1003/BSD | 02/01/2025 | 22/01/2025 | K.D ENTERPRISE. | 2.36 | 0 | 0 | 100
Total | [13 empty] | 22890.8 | 209.47 | 0.92