## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Hiring 1 (one) no. Diesel Luxary Car on daily basis (for 01.09.2024 to 28.02.2025) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. |  | Junior Engineer | ORD/001179/2024-2025 | 1121/BST | 30/08/2024 | 27/02/2025 | DEBAPRASAD MONDAL. | 0.86 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Formal work order for Construction of 700cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing FHTC for Augmentation of Berachampa Zone-I water supply Scheme under Barasat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000759/2023-2024 | 2552/BD | 24/08/2023 | 18/08/2024 | MONDAL ENTERPRISE. (BARASAT) | 777.6 | 0 | 0 | 24
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Berachampa Zone-I Water Supply Scheme within Deganga Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001154/2024-2025 | 99/BD | 09/01/2025 | 18/02/2025 | JAGANNATH CONSTRUCTION. | 9.19 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Acceptance cum work order for Construction of Boundary Wall in Hosenpur Mouza Water Supply Scheme at Berachampa Zone - I within Deganga Block under Barasat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001043/2024-2025 | 56/BD | 07/01/2025 | 06/02/2025 | JIT CONSTRUCTION | 27.29 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Acceptance cum work order for Additional Laying of HDPE pipe line and allied work in connection with Augmentation Berachampa Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001049/2024-2025 | 54/BD | 07/01/2025 | 06/02/2025 | MONDAL ENTERPRISE. (BARASAT) | 36.88 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2022-2023 | 658/BSD | 18/08/2022 | 17/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 3.86 | 100 | 1
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. X 200mm.dia. 190.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long filter for Augmentation of Berachampa Zone-I Water Supply Scheme at 2nd Tube well Site under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 2192/BD | 05/08/2024 | 04/09/2024 | M/S K.P.PAL. | 13.3 | 0 | 0 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-C | Assistant Engineer | Junior Engineer | ORD/001843/2023-2024 | 1119./BSD | 09/02/2024 | 13/02/2024 | S.M.TRADERS. | 0.88 | 0 | 0 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tube well by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-I Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001925/2023-2024 | 802/BD | 15/03/2024 | 14/04/2024 | ACME CONSTRUCTION | 13.08 | 0 | 0 | 80
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-I water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. |  | Junior Engineer | ORD/002151/2023-2024 | 1242/BSD | 15/03/2024 | 14/04/2024 | ROMI TREDERS. | 4.86 | 0 | 0 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1284/BD | 25/04/2023 |  | Resource Division | 211.19 | 0 | 0 | 0
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 3093/BD | 10/10/2023 |  | Resource Division | 24.61 | 0 | 0 | 0
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 4374/BD | 10/11/2023 |  | Resource Division | 9.49 | 0 | 0 | 0
14 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | New service connection at P.H.No- I ,Zone-I of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04807/2023-2024 | BP-306-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0 | null
15 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | SM/14490 | Augmentation | New service connection at P.H.No- I ,Zone-I of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04807/2023-2024 | BP-306-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0 | null
Total | [13 empty] | 1140.08 | 3.86 | 0.34