## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Sultanpur Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000768/2022-2023 | 632/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3 | 3 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sultanpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001158/2022-2023 | 698/BD | 03/03/2023 | 01/06/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 239.69 | 210.08 | 87.65 | 92
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Acceptance cum work order for Construction of approach road with cement concrete at PH No.-1 within Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2023-2024 | 1130/HSD | 05/09/2023 | 12/09/2023 | ANKUSH CONSTRUCTION & CO. | 1.83 | 1.64 | 89.82 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001980/2023-2024 | 917/BD | 15/03/2024 | 29/04/2024 | M/S B.K.ENTERPRISE. | 50.73 | 45.65 | 89.98 | 100
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Sultanpur W/S Scheme, Block-Hasnabad in District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001895/2023-2024 | 6757/EMD | 28/11/2023 | 01/06/2025 | DIPALI CONSTRUCTION | 26.48 | 19.39 | 73.24 | 70
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line & Providing FHTC for the leftout portion in connection with Augmentation of Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001395/2024-2025 | 261/HSD | 30/01/2025 | 09/02/2025 | M/S TAMAL CHAKRABORTY. | 0.97 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Sultanpur Piped water supply scheme | SM/14510 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Sultanpur water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001432/2024-2025 | 312/HSD | 04/02/2025 | 14/02/2025 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 100
Total | [13 empty] | 323.43 | 279.77 | 86.5