## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Bermajur Piped water supply scheme | SM/14511 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I, II, III and IV under Bermajur W/S Scheme, Block-Sandeshkhali-II in District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001890/2023-2024 | 6753/EMD | 28/11/2023 | 28/12/2023 | M/S DILIP MITRA | 43.15 | 0 | 0 | 60
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Bermajur Piped water supply scheme | SM/14511 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000476/2024-2025 | 2735/BD | 20/09/2024 | 20/10/2024 | M/S NIRMAN CONSTRUCTION. | 283.68 | 0 | 0 | 58
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Bermajur Piped water supply scheme | SM/14511 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Bermajur Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000770/2022-2023 | 634/HSD | 08/04/2022 | 23/04/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.32 | 4.32 | 100 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Bermajur Piped water supply scheme | SM/14511 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bermajur water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001166/2022-2023 | 701/BD | 03/03/2023 | 01/06/2023 | M/S DATTA ENTERPRISE. | 242.46 | 208.82 | 86.12 | 38
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Bermajur Piped water supply scheme | SM/14511 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001668/2023-2024 | 296/BD | 30/01/2024 | 15/03/2024 | M/S RAJPATH CONSTRUCTION. | 51.76 | 0 | 0 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Bermajur Piped water supply scheme | SM/14511 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000540/2024-2025 | 2929/BD | 03/10/2024 | 22/12/2024 | TITUMIR INTERNATIONAL | 51.66 | 0 | 0 | 100
Total | [13 empty] | 677.04 | 213.14 | 31.48