## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 2 & 3(at defunct T/W site) with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Hingalganj W/S(old) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000527/2022-2023 | 2242/BD | 22/08/2022 | 21/09/2022 | ACME CONSTRUCTION | 44.4 | 0 | 0 | 55
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 1203/BD | 20/04/2023 | 20/05/2023 | ANJALI ENTERPRISE. | 21.52 | 18.03 | 83.79 | 0
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I,II,II,IV and V (Zone-I) under Hingalganj Aug. W/S Scheme, Block-Hingalganj in District of 24 Pgs. (N) NIET No. 38 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/001933/2022-2023 | 1232/EMD | 24/03/2023 | 23/04/2023 | H.K. DAS & CO. | 53.44 | 41.39 | 77.45 | 77
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000548/2024-2025 | 3025/BD | 22/10/2024 | 20/01/2025 | M/S ANUBHAB CONSTRUCTION. | 15.83 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-II under Hingalganj Old ground water based water supply scheme under Block_ Hingalganj Dist. - 24 Pgs. (N) under EMD, PHE Dte. (SM/14512) | Assistant Engineer |  | ORD/000646/2024-2025 | 2683/EMD | 20/11/2024 | 20/12/2024 | H.K. DAS & CO. | 10.61 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Tapan Shit & Shyamal Samanta at Hingalganj in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer |  | ORD/000993/2024-2025 | 3497/BD | 11/12/2024 | 10/01/2025 | MD.SALIM GAZI. | 7.72 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Ajay Manna & Bijon Manna at Mamudpur in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000994/2024-2025 | 3498/BD | 11/12/2024 | 10/01/2025 | NURJAHAN ENTERPRISE. | 7.55 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000536/2024-2025 | 2902/BD | 03/10/2024 | 02/12/2024 | ANJALI ENTERPRISE. | 51.76 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of protection wall at OHR site, construction of approach road at OHR & CWR site & other allied works within within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2024-2025 | 2105/BD | 29/07/2024 | 27/10/2024 | SARKAR ENTERPRISE & CO. | 12.93 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - I Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000771/2022-2023 | 635/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001157/2022-2023 | 697/BD | 03/03/2023 | 01/06/2023 | M/S PROGATI ENTERPRISE. | 296.42 | 251.35 | 84.8 | 53
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000732/2023-2024 | 2480/BD | 18/08/2023 | 17/09/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 51.64 | 0 | 0 | 100
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000733/2023-2024 | 2482/BD | 18/08/2023 | 17/09/2023 | MONDAL & CO. (BASIRHAT). | 51.6 | 0 | 0 | 100
14 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Mamudpur mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001801/2023-2024 | 220/HSD | 29/02/2024 | 10/03/2024 | TRISHA ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
15 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hingalganj mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001800/2023-2024 | 219/HSD | 29/02/2024 | 10/03/2024 | MONDAL & CO. (BASIRHAT). | 0.97 | 0 | 0 | 100
Total | [13 empty] | 632.14 | 315.6 | 49.93