## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 2 & 3(at defunct T/W site) with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Hingalganj W/S(old) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000527/2022-2023 | 2242/BD | 22/08/2022 | 21/09/2022 | ACME CONSTRUCTION | 44.4 | 16.89 | 38.04 | 55
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - I Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000771/2022-2023 | 635/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 1203/BD | 20/04/2023 | 20/05/2023 | ANJALI ENTERPRISE. | 21.52 | 18.03 | 83.79 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001157/2022-2023 | 697/BD | 03/03/2023 | 01/06/2023 | M/S PROGATI ENTERPRISE. | 296.42 | 288.69 | 97.39 | 53
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I,II,II,IV and V (Zone-I) under Hingalganj Aug. W/S Scheme, Block-Hingalganj in District of 24 Pgs. (N) NIET No. 38 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/001933/2022-2023 | 1232/EMD | 24/03/2023 | 01/04/2025 | H.K. DAS & CO. | 53.44 | 41.39 | 77.45 | 77
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000732/2023-2024 | 2480/BD | 18/08/2023 | 17/09/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 51.64 | 38.28 | 74.14 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000733/2023-2024 | 2482/BD | 18/08/2023 | 17/09/2023 | MONDAL & CO. (BASIRHAT). | 51.6 | 38.01 | 73.67 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000250/2022-2023 | 929/BD | 22/03/2023 | 22/03/2023 | Resource Division | 50.77 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000548/2024-2025 | 3025/BD | 22/10/2024 | 20/01/2025 | M/S ANUBHAB CONSTRUCTION. | 15.83 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Ajay Manna & Bijon Manna at Mamudpur in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000994/2024-2025 | 3498/BD | 11/12/2024 | 10/01/2025 | NURJAHAN ENTERPRISE. | 7.55 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000536/2024-2025 | 2902/BD | 03/10/2024 | 02/12/2024 | ANJALI ENTERPRISE. | 51.76 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Mamudpur mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001801/2023-2024 | 220/HSD | 29/02/2024 | 10/03/2024 | TRISHA ENTERPRISE & CO. | 0.94 | 0.93 | 98.98 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hingalganj mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001800/2023-2024 | 219/HSD | 29/02/2024 | 10/03/2024 | MONDAL & CO. (BASIRHAT). | 0.97 | 0.97 | 99.93 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of protection wall at OHR site, construction of approach road at OHR & CWR site & other allied works within within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2024-2025 | 2105/BD | 29/07/2024 | 28/01/2025 | SARKAR ENTERPRISE & CO. | 12.93 | 0 | 0 | 100
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-II under Hingalganj Old ground water based water supply scheme under Block_ Hingalganj Dist. - 24 Pgs. (N) under EMD, PHE Dte. (SM/14512) | Assistant Engineer | Junior Engineer | ORD/000646/2024-2025 | 2683/EMD | 20/11/2024 | 01/05/2025 | H.K. DAS & CO. | 10.61 | 0 | 0 | 100
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Tapan Shit & Shyamal Samanta at Hingalganj in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000993/2024-2025 | 3497/BD | 11/12/2024 | 10/05/2025 | MD.SALIM GAZI. | 7.72 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Construction of Pressure sand filter of capacity 120 cum/hr at Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000190/2025-2026 | 2023/BD | 18/06/2025 | 15/11/2025 | FIDERE MARINE SERVICES PVT. LTD. | 38.29 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at near primary school at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000141/2025-2026 | 991/HSD | 04/06/2025 | 14/06/2025 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001457/2024-2025 | 94/BD | 08/01/2025 | 22/01/2025 | MONDAL & CO. (BASIRHAT). | 13.34 | 0 | 0 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at 8 no Khatuapara SSK, Keorakhali FP School and Sahapur FP School within the command area of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2025-2026 | 1482/HSD | 14/07/2025 | 24/07/2025 | M/S RAJPATH CONSTRUCTION. | 0.64 | 0 | 0 | 100
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent laying of 90 mm dia UPVC pipe line for damage portion at N/H/O Ex Sabhapati Sudip Mondal, Hingalganj with retrofitting work in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2025-2026 | 1000/HSD | 04/06/2025 | 14/06/2025 | TRISHA ENTERPRISE & CO. | 0.87 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Supply and installation of 100 mm dia sluice valve at different washout point in distribution pipe line for smooth supply of water in connection with augmentation of Hingalganj water supply scheme Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000254/2025-2026 | 2331/BD | 07/07/2025 | 06/08/2025 | MONDAL & CO. (BASIRHAT). | 5.91 | 0 | 0 | 100
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at near PH No-3 within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001902/2024-2025 | 538/HSD | 10/03/2025 | 20/03/2025 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at N/H/O Prodip Mondal at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2025-2026 | 937/HSD | 29/05/2025 | 08/06/2025 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
25 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Hingalganj water supply scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001331/2024-2025 | 175/HSD | 27/01/2025 | 06/02/2025 | MD.SALIM GAZI. | 0.55 | 0.55 | 100 | 100
26 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent providing of 2 nos. FHTC at Hingalganj Krishimandi with laying of 63 mm dia UPVC pipe line in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001333/2024-2025 | 177/HSD | 27/01/2025 | 06/02/2025 | MD.SALIM GAZI. | 0.51 | 0.51 | 99.74 | 100
27 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at N/H/O Ration Dealer at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2025-2026 | 994/HSD | 04/06/2025 | 14/06/2025 | MONDAL & CO. (BASIRHAT). | 0.96 | 0 | 0 | 100
28 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at near ICDS at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000157/2025-2026 | 1002/HSD | 04/06/2025 | 14/06/2025 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
29 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | Acceptance cum work order for Emergent restoration of 90 mm dia UPVC pipeline at Jora Battala Hingalganj due to construction of road in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000259/2025-2026 | 2330/BD | 07/07/2025 | 06/08/2025 | TRISHA ENTERPRISE & CO. | 8.11 | 0 | 0 | 100
30 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I | SM/14512 | Augmentation | 11 KV New Service Connection at OHR site of Zone-I under Hingalganj Augmentation W/S scheme |  |  | BILL/02662/2024-2025 | BP-242 | 04/02/2025 | 04/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.69 | 0 | 0 | 0
Total | [13 empty] | 761.63 | 449.08 | 58.96