## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - II Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2022-2023 | 636/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.39 | 4.39 | 100 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001161/2022-2023 | 700/BD | 03/03/2023 | 01/06/2023 | M/S NIRMAN CONSTRUCTION. | 313.44 | 291.97 | 93.15 | 40
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-5 & 6 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000735/2023-2024 | 2489/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 51.63 | 38.75 | 75.06 | 100
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III, IV,V and VI (Zone-II) (Rep.) under Hingalganj Aug. W/S Scheme, Block- Hingalganj in District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001905/2023-2024 | 6773/EMD | 29/11/2023 | 01/06/2025 | M.S. ENTERPRISE | 63 | 18.79 | 29.83 | 32
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at pond of Monojit Gayen and near shop of Abdul Alim Gazi in connection with Augmentation of Hingalganj W/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 3500/BD | 11/12/2024 | 10/01/2025 | S.K.ENTERPRISE. | 8.64 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000537/2024-2025 | 2903/BD | 03/10/2024 | 02/12/2024 | M/S RAJPATH CONSTRUCTION. | 51.59 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Abdul Dhali & Anar Dhali in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000996/2024-2025 | 3499/BD | 11/12/2024 | 11/06/2027 | SARKAR ENTERPRISE | 8.51 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Rabiul Gazi & Enamul Gazi in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000995/2024-2025 | 3740/BD | 27/12/2024 | 26/01/2025 | CHITTARANJAN MONDAL | 8.19 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001680/2023-2024 | 527/BD | 20/02/2024 | 01/04/2025 | UTPAL CONSTRUCTION & CO. | 49.99 | 11.99 | 23.99 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for inking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001684/2023-2024 | 525/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 49.99 | 38.62 | 77.26 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-5 & 6 in connection with Augmentation for Hingalganj w/s (Z-II) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001845/2023-2024 | 271/HSD | 06/03/2024 | 16/03/2024 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0.96 | 99.86 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection for Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001415/2024-2025 | 145/BD | 13/01/2025 | 29/03/2025 | ABDUL HAMID GAZI. | 10.59 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Biswajit Ghosh & other places in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000054/2025-2026 | 1613/BD | 19/05/2025 | 18/06/2025 | ANKUSH CONSTRUCTION & CO. | 12.24 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000028/2025-2026 | 1428/BD | 06/05/2025 | 04/08/2025 | SUPER ENTERPRISE | 14.14 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 4 & 8 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001518/2024-2025 | 381/HSD | 10/02/2025 | 20/02/2025 | S.K.ENTERPRISE. | 0.96 | 0 | 0 | 100
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at 11 no Sandelerbill FP School, 9 no Purba Sandeslerbill FP School, Dakshin Bankra Sarkarpara SSk, Sandelerbill Jr. High School and Tarinipur SSK within the command area of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001911/2024-2025 | 544/HSD | 10/03/2025 | 20/03/2025 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001421/2024-2025 | 164/BD | 14/01/2025 | 04/02/2025 | S.K.ENTERPRISE. | 14.45 | 3.82 | 26.46 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 14 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001330/2024-2025 | 174/HSD | 27/01/2025 | 06/02/2025 | M/S NIRMAN CONSTRUCTION. | 0.96 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 11 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001335/2024-2025 | 179/HSD | 27/01/2025 | 06/02/2025 | M/S NIRMAN CONSTRUCTION. | 0.96 | 0 | 0 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 9 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001337/2024-2025 | 181/HSD | 27/01/2025 | 06/02/2025 | M/S NIRMAN CONSTRUCTION. | 0.96 | 0 | 0 | 100
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Singherkati mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001367/2024-2025 | 234/HSD | 30/01/2025 | 09/02/2025 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.96 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Bankra mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001519/2024-2025 | 382/HSD | 10/02/2025 | 20/02/2025 | S.K.ENTERPRISE. | 0.96 | 0 | 0 | 100
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Uttar Bankra Dobar in Bankra Dobar mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001610/2024-2025 | 474/HSD | 28/02/2025 | 10/03/2025 | S.K.ENTERPRISE. | 0.96 | 0 | 0 | 100
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Dakshin Bankra Dobar in Bankra Dobar mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001434/2024-2025 | 314/HSD | 04/02/2025 | 14/02/2025 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.96 | 0 | 0 | 100
Total | [13 empty] | 670.4 | 409.3 | 61.05