## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III, IV,V and VI (Zone-II) (Rep.) under Hingalganj Aug. W/S Scheme, Block- Hingalganj in District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001905/2023-2024 | 6773/EMD | 29/11/2023 | 01/02/2025 | M.S. ENTERPRISE | 63 | 0 | 0 | 32
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001680/2023-2024 | 527/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 49.99 | 0 | 0 | 50
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at pond of Monojit Gayen and near shop of Abdul Alim Gazi in connection with Augmentation of Hingalganj W/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000997/2024-2025 | 3500/BD | 11/12/2024 | 10/01/2025 | S.K.ENTERPRISE. | 8.64 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Abdul Dhali & Anar Dhali in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000996/2024-2025 | 3499/BD | 11/12/2024 | 30/05/2027 | SARKAR ENTERPRISE | 8.51 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Rabiul Gazi & Enamul Gazi in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000995/2024-2025 | 3740/BD | 27/12/2024 | 26/01/2025 | CHITTARANJAN MONDAL | 8.19 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - II Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2022-2023 | 636/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.39 | 4.39 | 100 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001161/2022-2023 | 700/BD | 03/03/2023 | 01/06/2023 | M/S NIRMAN CONSTRUCTION. | 313.44 | 239.91 | 76.54 | 40
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-5 & 6 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000735/2023-2024 | 2489/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 51.63 | 19.38 | 37.53 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for inking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001684/2023-2024 | 525/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 49.99 | 0 | 0 | 100
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II | SM/14513 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-5 & 6 in connection with Augmentation for Hingalganj w/s (Z-II) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001845/2023-2024 | 271/HSD | 06/03/2024 | 16/03/2024 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0 | 0 | 100
Total | [13 empty] | 558.73 | 263.67 | 47.19