## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Supply & delivery of submersible pump motor set and installed the same of P/H No. I & II under Chhota Sehara water supply scheme Dist- 24 Pgs(N). T.No. 110/SD I 23.24 Dt. 05.04.23 W.o. dt. 31.05.23 |  |  | ORD/002685/2022-2023 | 1332/SDI | 14/08/2022 | 13/09/2022 | S.B.ENTERPRISE | 1.72 | 0 | 0 | 30
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I & II under Chhoto Sehara W/S Scheme, Block-Sandeshkhali-I in District of 24 Pgs. (N) |  |  | ORD/001892/2023-2024 | 6754/EMD | 28/11/2023 | 28/12/2023 | P.K. ENGINEERING | 22.29 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Chhoto Sehara Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000767/2022-2023 | 631/HSD | 08/04/2022 | 23/04/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.78 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001201/2022-2023 | 830/BD | 15/03/2023 | 13/06/2023 | MONDAL & CO. (BASIRHAT). | 227.81 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Supply & delivery of submersible pump moter set and istalled the same of P/H No. I & II under Chhota Sehara water supply scheme Dist- 24 Pgs(N). | Assistant Engineer | Junior Engineer | ORD/000044/2023-2024 | 1332/EMSD-I | 31/05/2023 | 15/06/2023 | S.B.ENTERPRISE | 1.72 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/001355/2022-2023 | 1153/BD. | 12/04/2022 | 08/12/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 143.13 | 0 | 0 | 95
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Additional work in connection with Supply & delivery of submersible pump moter and installed the same at P H No. I & II of Chhota Sehara water supply scheme under Eastern Mechanical Sub Division-I, PHE Dte. Dist- 24 Pgs(N) |  |  | ORD/001193/2023-2024 | 1785/EMSD-I | 10/08/2023 | 17/08/2023 | S.B.ENTERPRISE | 1.29 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Providing outdoor illumination arrangement at PH-I & II under chhota sehara W/S Scheme. |  |  | ORD/002732/2022-2023 | 744EMD | 14/03/2023 | 13/04/2023 | M/S. G.P. ENTERPRISE | 2.17 | 0 | 0 | 90
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000242/2022-2023 | 936/BD | 22/03/2023 | 22/03/2023 | Resource Division | 28.95 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme | SM/14514 | Augmentation | Formal work order for Additional laying of 160 mm dia. HDPE pipe line from old pump house no- 3 to near Putimari Ghat, protection works & other allied works within Kalinagar w/s scheme (Z-II), Sandeshkhali-I Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001056/2024-2025 | 3714/BD | 26/12/2024 | 24/06/2025 | M/S JAYDEEP DASGUPTA | 151.37 | 0 | 0 | 35
Total | [13 empty] | 583.23 | 0 | 0