## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I and II (Rep.) under Rajbari W/S Scheme, Block-Sandeshkhali-I in District of 24 Pgs. (N) NIET No. 38 of EE/EMD of 2022-23 (Sl. No.- 07) |  |  | ORD/001676/2022-2023 | 1014/EMD | 09/03/2023 | 08/04/2023 | BARISAL TRADING CO. | 21.23 | 19.49 | 91.82 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Rajbari Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2022-2023 | 633/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.72 | 3.72 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 2 for Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000292/2023-2024 | 796/HSD | 13/07/2023 | 20/07/2023 | SAGAR DAS. | 0.62 | 0.56 | 90.46 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000243/2022-2023 | 940/BD | 22/03/2023 | 22/03/2023 | Resource Division | 25.03 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Formal work order for for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajbari water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2022-2023 | 829/BD | 15/03/2023 | 13/06/2023 | M/S DATTA ENTERPRISE. | 279.81 | 277.17 | 99.06 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Repairing of Pump house and Dismantling, Re-construction of boundary wall and approach road for movement of rig & other machineries for sinking of big dia. TW at PH no- 1 in connection with Augmentation of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000907/2023-2024 | 2718/BD | 05/09/2023 | 26/09/2023 | M/S ANUBHAB CONSTRUCTION. | 5.06 | 4.45 | 87.83 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Rajbari Purbapara SSK & Paschim Laukhali Sobahan Molla Smriti FP School, within the command area of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/001918/2024-2025 | 545/HSD | 10/03/2025 | 20/03/2025 | SARKAR ENTERPRISE | 0.5 | 0 | 0 | 0
Total | [13 empty] | 335.97 | 305.39 | 90.9