## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Rajbari Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2022-2023 | 633/HSD | 08/04/2022 | 23/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.72 | 3.72 | 100 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I and II (Rep.) under Rajbari W/S Scheme, Block-Sandeshkhali-I in District of 24 Pgs. (N) NIET No. 38 of EE/EMD of 2022-23 (Sl. No.- 07) |  |  | ORD/001676/2022-2023 | 1014/EMD | 09/03/2023 | 08/04/2023 | BARISAL TRADING CO. | 21.23 | 19.49 | 91.82 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Formal work order for for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajbari water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2022-2023 | 829/BD | 15/03/2023 | 13/06/2023 | M/S DATTA ENTERPRISE. | 279.81 | 277.17 | 99.06 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Repairing of Pump house and Dismantling, Re-construction of boundary wall and approach road for movement of rig & other machineries for sinking of big dia. TW at PH no- 1 in connection with Augmentation of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000907/2023-2024 | 2718/BD | 05/09/2023 | 26/09/2023 | M/S ANUBHAB CONSTRUCTION. | 5.06 | 4.45 | 87.83 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 2 for Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000292/2023-2024 | 796/HSD | 13/07/2023 | 20/07/2023 | SAGAR DAS. | 0.62 | 0.56 | 90.46 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000243/2022-2023 | 940/BD | 22/03/2023 | 22/03/2023 | Resource Division | 25.03 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Rajbari water supply scheme (Z-I), Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000697/2024-2025 | 3182/BD | 18/11/2024 | 17/01/2025 | M/S K.B.ENTERPRISE. | 60.6 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Rajbari Purbapara SSK & Paschim Laukhali Sobahan Molla Smriti FP School, within the command area of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/001918/2024-2025 | 545/HSD | 10/03/2025 | 20/03/2025 | SARKAR ENTERPRISE | 0.5 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Rajbari Piped water supply scheme | SM/14515 | Augmentation | Acceptance cum work order for Protection of different dia. UPVC pipeline by UC bullah pile near PH No- 1 in connection with augmentation of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2025-2026 | 843/HSD | 15/05/2025 | 25/05/2025 | M/S ANUBHAB CONSTRUCTION. | 1.33 | 0 | 0 | 100
Total | [13 empty] | 397.9 | 305.39 | 76.75