## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14542 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 4024/BD | 12/10/2023 | 12/10/2023 | Resource Division | 123.26 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | SM/14542 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area & Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works at Head work site of Zone-I within Amdanga Block of surface based Water Supply Scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001177/2023-2024 | 3007/BD | 05/10/2023 | 03/01/2024 | KINGS & CO. | 894.25 | 0 | 0 | 0
Total | [13 empty] | 1017.51 | 0 | 0