## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. dia. 300 mtr deep as a Replacement of Tubewell by D.R. Rig method, having 250mm dia 36.0 mtr. long UPVC housing pipe & 150mm dia 30 mtr. long UPVC ribbed strainer for Augmentation of Kashimpur Water Supply Scheme at Head Work Site under Barasat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000683/2023-2024 | 2460/BD | 17/08/2023 | 16/09/2023 | M/S K.P.PAL. | 16.08 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1671/BD | 06/06/2023 | 06/06/2023 | Resource Division | 9.76 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1282/BD | 25/04/2023 | 25/04/2023 | Resource Division | 13.18 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Acceptance cum work order for Hiring diesel luxury car daily basis (From 22.11.2023 to 31.05.2024) for the Office uses of the Assistant Engineer (HQ) Barasat Division, P.H.Dte. | Assistant Engineer |  | ORD/001422/2023-2024 | 4461/BD | 21/11/2023 | 31/05/2024 | KRISHNA SAHA. | 0.91 | 0 | 0 | 18
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-01-2024 to 31-03-2024). | Assistant Engineer | Junior Engineer | ORD/001461/2023-2024 | 4696/BD | 12/12/2023 | 12/03/2024 | DIPANKAR NASKAR. | 0.43 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Acceptance cum work order for Hiring diesel luxury car daily basis (From 01.06.2024 to 30.11.2024) for the Office uses of the Assistant Engineer (HQ) Barasat Division, P.H.Dte. | Assistant Engineer |  | ORD/002257/2023-2024 | 845/BD | 13/03/2024 | 12/09/2024 | KRISHNA SAHA. | 0.87 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-04-2024 to 30-09-2024). | Assistant Engineer | Junior Engineer | ORD/001928/2023-2024 | 914/BD | 15/03/2024 | 14/09/2024 | DIPANKAR NASKAR. | 0.87 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Preparation of DPR in connection of augumentation of Kashimpur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2022-2023 | 666/BSD | 25/08/2022 | 24/09/2022 | RADIANT | 3.04 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Formal work order for Construction of 200 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Kashimpur water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 1716/BD | 08/06/2023 | 08/06/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 318.43 | 0 | 0 | 90
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Kashimpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001143/2023-2024 | 4746/EMD | 07/08/2023 | 06/09/2023 | MAHAMAYA ENTERPRISE. | 26.07 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. big dia. 210 mtr deep Tubewell by D.R. Rig method having 250 mm dia 42.0 mtr. long PVC housing pipe & 150 mm dia 30.0 mtr. long filter for Augmentation Kashimpur Water Supply Scheme (2nd T/W Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001770/2023-2024 | 587/BD | 23/02/2024 | 24/03/2024 | SUBHAJIT SAHA | 11.22 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001853/2023-2024 | 1121./1/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | SM/14733 | Augmentation | Different works in connection with Augmentation Kashimpur PWSS (1st Tubewell site - Pump House). | Assistant Engineer | Junior Engineer | ORD/000471/2024-2025 | 586/BSD | 10/09/2024 | 30/09/2024 | K.C. ENTERPRISE | 3.53 | 0 | 0 | 100
Total | [13 empty] | 405.28 | 0 | 0