## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-IV under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000610/2022-2023 | 671/BSD | 29/08/2022 | 28/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.95 | 3.95 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 4371/BD | 10/11/2023 | 10/11/2023 | Resource Division | 94.42 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 3086/BD | 10/10/2023 | 10/10/2023 | Resource Division | 28.89 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1278/BD | 25/04/2023 | 25/04/2023 | Resource Division | 197.95 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at Nandipara Kuchemora Under Berachampa Zone-IV Water Supply Scheme under Deganga Block, under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000992/2024-2025 | 3476/BD | 10/12/2024 | 09/01/2025 | JP CONSTRUCTION & SUPPLIERS. | 32.77 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-F | Assistant Engineer | Junior Engineer | ORD/001849/2023-2024 | 1120./1/BSD | 09/02/2024 | 13/02/2024 | S.M.TRADERS. | 0.87 | 0.87 | 100 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-IV water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. |  | Junior Engineer | ORD/002153/2023-2024 | 1244/BSD | 15/03/2024 | 15/04/2024 | M/S S.HAQUE & CO. | 4.88 | 4.87 | 99.96 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. X 200mm.dia. 190.00mtr. deep tubewell by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long filter for Augumentation of Berachampa Zone-IV Water Supply Scheme at OHR Site under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000280/2024-2025 | 2193/BD | 05/08/2024 | 04/09/2024 | ANJALI ENTERPRISE. | 13.3 | 3.48 | 26.17 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | New service connection at P.H.No- I Zone-IV of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04803/2023-2024 | BP-307-23-24 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.05 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Formal work order for Construction of 700 cum capacity 20mtr staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Berachampa Zone-IV Water Supply scheme under Barasat Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001204/2023-2024 | 4018/BD | 12/10/2023 | 11/10/2025 | A.P POWER & CONCRETE | 877.47 | 197.2 | 22.47 | 30
11 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 29.42 | 0.14 | 11
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | SM/15323 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I, II and IV) under Berachampa W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000823/2022-2023 | 30/EMDdt.03.01.2023 | 10/02/2023 | 01/07/2025 | M/S P.P. ELECTRICALS | 78.21 | 0 | 0 | 66
Total | [13 empty] | 22675.52 | 239.8 | 1.06