## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A). | Assistant Engineer | Junior Engineer | ORD/002744/2021-2022 | 348/HSD | 21/02/2022 | 08/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002745/2021-2022 | 349/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 0 | 0 | 1
3 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Material Requisition To Resource Division |  |  | RTOR000232/2022-2023 | 868/BD | 22/03/2023 | 22/03/2023 | Resource Division | 23.84 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Mathbari Abad W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000900/2023-2024 | 2704/BD | 04/09/2023 | 02/09/2026 | M/S DATTA ENTERPRISE. | 442.43 | 0 | 0 | 85
5 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily hire basis for use of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.11.23 to 30.04.24 | Assistant Engineer | Junior Engineer | ORD/002507/2023-2024 | 1315/HSD | 30/10/2023 | 30/04/2024 | RANJIT KUMAR MANDAL | 0.86 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/002520/2023-2024 | ABDULALIMMONDAL | 09/01/2024 | 19/01/2024 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Mathbari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001910/2023-2024 | 282/HSD | 06/03/2024 | 16/03/2024 | M/S DATTA ENTERPRISE. | 0.84 | 0 | 0 | 22
8 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Supply and installation of 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000585/2024-2025 | 1171/HSD | 26/09/2024 | 06/10/2024 | ANKUSH CONSTRUCTION & CO. | 0.79 | 0 | 0 | 100
9 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with UC Bullah pilling at different places at Boyermari within Mathbari Abad w/s scheme (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000563/2024-2025 | 1003/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 0 | 100
10 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000554/2024-2025 | 996/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0 | 0 | 100
11 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Supply and installation of 200 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000558/2024-2025 | 1000/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.79 | 0 | 0 | 100
12 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with UC Bullah pilling at different places at Khas Sankardaha & Sankardaha Abad within Mathbari Abad w/s scheme (Scheme code-SM/15825), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000566/2024-2025 | 1006/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 0 | 100
13 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Emergent restoration of road for damage portion at different places in connection with retrofitting of Boyermari within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2024-2025 | 992/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0 | 100
14 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with bamboo pilling at different places at Khas Sankardaha & Sankardaha Abad within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000556/2024-2025 | 998/HSD | 29/08/2024 | 08/09/2024 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0 | 0 | 100
15 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002521/2023-2024 | 35/HSD. | 09/01/2024 | 19/01/2024 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 100
16 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002482/2023-2024 | 36/HSD | 09/01/2024 | 19/01/2024 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 100
17 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Supply and installation of 250 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000583/2024-2025 | 1160/HSD | 25/09/2024 | 05/10/2024 | ANKUSH CONSTRUCTION & CO. | 0.83 | 0 | 0 | 100
18 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with bamboo pilling at different places at Boyermari within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2024-2025 | 1178/HSD | 30/09/2024 | 10/10/2024 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 0 | 100
19 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Quotation for Service Connection Charges for PH- I under Mathbari Abad W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05538/2023-2024 | BP-364-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.37 | 0 | 0 | 0
20 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Service connection charges at PH-II under Mathbari Abad W/S Scheme |  |  | BILL/04756/2023-2024 | BP-295-23-24 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.79 | 0 | 0 | 0
21 | NORTH 24 PARGANAS | Sandeshkhali-I | Central Drilling | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
22 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Mathbari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000524/2024-2025 | 2796/BD | 25/09/2024 | 24/12/2024 | M/S PROGATI ENTERPRISE. | 140.81 | 0 | 0 | 70
23 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Construction of anchor block for resting of 250/200 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at different places for Mathbari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000262/2025-2026 | 2348/BD | 08/07/2025 | 06/09/2025 | M/S DATTA ENTERPRISE. | 6.1 | 0 | 0 | 0
Total | [13 empty] | 21985.99 | 0 | 0