## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Hasnabad | Eastern Mechanical | Katakhali Piped Water Supply Scheme | SM/15826 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No. I and II under Katakhali WS Scheme Block-Hasnabad New District of 24 Pgs. N |  |  | ORD/001220/2023-2024 | 4887/EMD | 14/08/2023 | 13/09/2023 | CINZANO | 21.42 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KATAKHALI Water Supply Scheme) in HASNABAD BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002689/2021-2022 | 231/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KATAKHALI Water Supply Scheme) in HASNABAD BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002690/2021-2022 | 232/HSD | 02/02/2022 | 17/02/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.01 | 4.01 | 100 | 1
4 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Material Requisition To Resource Division |  |  | RTOR000228/2022-2023 | 871/BD | 22/03/2023 | 22/03/2023 | Resource Division | 249.11 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2, 3 & 4 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr.staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Katakhali water supply scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 1729/BD | 08/06/2023 | 01/04/2026 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 389.24 | 273.03 | 70.14 | 100
6 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Formal work order for Additional Laying of DI Rising main & UPVC distribution pipe line, protection works & other allied works within Katakhali w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000407/2024-2025 | 2738/BD | 20/09/2024 | 18/05/2025 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 211.44 | 56.21 | 26.58 | 75
7 | NORTH 24 PARGANAS | Hasnabad | Eastern Mechanical | Katakhali Piped Water Supply Scheme | SM/15826 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No. III under Katakhali WS Scheme Block-Hasnabad New District of 24 Pgs. North | Assistant Engineer | Junior Engineer | ORD/001219/2023-2024 | 4875/EMD | 14/08/2023 | 13/09/2023 | GANAPATI ENTERPRISE | 10.61 | 0 | 0 | 90
8 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Acceptance cum work order for Construction of boundary wall with column structure at PH No-- 2, 3 & 4 within Katakhali w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/002258/2024-2025 | 1028/BD | 28/03/2025 | 26/06/2025 | R B ENTERPRISE | 25.44 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Hasnabad | Barasat Division | Katakhali Piped Water Supply Scheme | SM/15826 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1,2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Katakhali w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000862/2024-2025 | 3371/BD | 02/12/2024 | 02/03/2025 | SHIBU BISWAS. | 77.65 | 0 | 0 | 100
10 | NORTH 24 PARGANAS | Hasnabad | Eastern Mechanical | Katakhali Piped Water Supply Scheme | SM/15826 | New | New Service Connection Charges for PH-III under Katakhali W/S Scheme, Hingalganj CCC |  |  | BILL/02714/2024-2025 | BP-298 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.61 | 0 | 0 | 0
11 | NORTH 24 PARGANAS | Hasnabad | Eastern Mechanical | Katakhali Piped Water Supply Scheme | SM/15826 | New | New Service Connection Charges for PH-IV under Katakhali W/S Scheme, Hingalganj CCC |  |  | BILL/02715/2024-2025 | BP-297 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0 | 0
12 | NORTH 24 PARGANAS | Hasnabad | Eastern Mechanical | Katakhali Piped Water Supply Scheme | SM/15826 | New | New Service Connection Charges for PH-II under Katakhali W/S Scheme, Hingalganj CCC |  |  | BILL/02713/2024-2025 | BP-299 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.93 | 0 | 0 | 0
Total | [13 empty] | 1008.06 | 338.07 | 33.54